## EMIS OPERATIONAL PLAN R4
MoE EMIS OPERATIONAL PLAN R4
Original Plan Endorsed July 2020
Revised Plan Under Discussion June 2021
No. | REQUESTED BY | ACTIVITY TYPE | TARGET MOE FUNCTION | ACTIVITY/TASK | Description | CAPACITY DEVELOPMENT APPROACH | PREREQUISITE(S) | ROLES AND RESPONSIBILITIES | MEASURE OF ACHIEVEMENT | Status | Start Date | End Date | Adjusted PRIORITY | Q3 2020 | Q4 2020 |  |  | Q1 2021 |  |  | Q2 2021 |  |  | Q3 2021 |  |  | Q4 2021 |  |  | Q1 2022 |  |  | Q2 2022 |  |  | Q3 2022 |  |  | Q4 2022 |  |  | Q1 2023
[14 empty] | Sep M1 | Oct M2 | Nov M3 | Dec M4 | Jan M5 | Feb M6 | Mar M7 | Apr M8 | MayM9 | Jun M10 | Jul M11 | Aug M12 | Sep M13 | Oct M14 | Nov M15 | Dec M16 | Jan M17 | Feb M18 | Mar M19 | Apr M20 | MayM21 | Jun M22 | Jul M23 | Aug M24 | Sep M25 | Oct M26 | Nov M27 | Dec M28 | Jan M29 | Feb M30
Expected Result 1 - Improved OpenEMIS System Soundness
Output 1.1: Improved OpenEMIS system, security and data architecture
1.1.1 | QRC | EMIS Feature Enhancement | Data and information management | Upgrade of all OpenEMIS components to their latest version (2b-1) | OpenEMIS was not upgraded for more than 2 years. Upgrade is applicable for Core, Integrator, Data manager, Dashboard and Monitoring. It is going to take some time and thus needs to be planned carefully to avoid interruption of critical EMIS operations within school year. • Best period identified by QRC: between 1july and 31 august. | Project initial software upgrade operations will be conducted with active participation of QRC and technical backstopping from UNESCO and system administration local service provider. QRC team will then be encouraged to lead the recurrent upgrade process within phase II time frame (see activity 2) | • Hardware upgrade completed by MoE (at least SAN storage) • An active system administration MoE contract with local company (ex: PALCO) • OpenEMIS Core backup file provided to UNESCO/CSF prior start of the activity to test the upgrade process in the Lab • The ability to shutdown the system for 3 weeks minimum | • QRC finalizes hardware procurement • UNESCO/CSF provides upgrade scripts • Local system administration company (ex:PALCO) and QRC run upgrade scripts for software and DBs on local UAT hardware • UNESCO provides technical backstopping for QRC team • QRC approves proposed upgrade • Local system administration (ex: PALCO) and QRC apply upgrade on PROD | OpenEMIS version number on JOR servers is the latest | Ongoing | 2020-09-01 | 2021-09-01 | Critical | bar: Q3 2020 Sep M1 to Q3 2021 Sep M13
1.1.2 | QRC | Capacity Development | Data and information management | On-the-job capacity building and technical assistance on management of OpenEMIS software upgrade process (2b-2) | QRC System Administration Team needs to be able to professionally deploy future free OpenEMIS releases to the Jordan EMIS. | This activity will provide on-the-job technical assistance and capacity building to the QRC team to learn the process by doing. | • QRC System Administration Team members identified • An active system administration MoE contract with local company (ex: PALCO) • Hardware upgrade completed (at least SAN storage) | • QRC downloads OpenEMIS update scripts and implements OpenEMIS software upgrade process tasks • UNESCO/CSF and local system administration (ex: PALCO) provide technical backstopping and on-the-job training | • Number of OpenEMIS upgrades • % of OpenEMIS upgrades achieved by QRC without external technical assistance. | Ongoing | 2020-09-01 | 2023-02-01 | Critical | bar: Q3 2020 Sep M1 to Q1 2023 Feb M30
1.1.3a | QRC | EMIS Feature Enhancement | Data and information management | Improvement of the EMIS system architecture to address security issues highlighted by MoDEE regular security testings (2b-3) | from the initial security audit, out of 10 items identified, 3 relate to OpenEMIS software and can be fixed by simple upgrade of the software to latest version; 1 requires development of a Content Management System by QRC for the landing page of the EMIS website and 6 can be fixed by upgrading and configuration of the hardware and server operating system. continous improvement will be performed as required based on results of regular security testings | This activity will be supervised by QRC with the support of MoDEE and system administration services provider | Activity 1.1.1 | • MoE procures WAF hardware • Local Hardware supplier installs WAF • QRC deploys a new CMS for Wiki content with UNESCO's assistance • Local system administration company (ex: PALCO) enhances the operating system configurations on servers | • % of security issues solved • EMIS Portal landing page content managed by a new CMS | Ongoing | 2021-10-01 | 2022-08-01 | Critical | bar: Q4 2021 Oct M14 to Q3 2022 Aug M24
1.1.3b | QRC | EMIS Feature Enhancement | Data and information management | Perform regular security testing on OpenEMIS core production environment and address security issues highlighted in the testing | MoE will secure the services of a specialist 3rd party to perform regular security testing on OpenEMIS core production | This activity will be supervised by MoE with the support of MoDEE and system administration services provider | Activity 1.1.3a | • MoE to request support from MODEE to perform the regular testing • MODEE to assign a 3rd party to perform the test in coordination with QRC • QRC to address the findings of the test | • security test report | Not started | 2021-09-01 | 2022-11-01 | High | bar: Q3 2021 Sep M13; Q4 2022 Nov M27
1.1.4a | QRC | Capacity Development | Data and information management | Training on OpenEMIS APIs (2b-4) | This 5 days course for the QRC/EMIS system administration team focuses on the presentation and use of secured OpenEMIS Application Programming Interfaces (APIs) to enable creation of software applications outside of OpenEMIS that access the features or data available in OpenEMIS. | This course will enable MoE and its partner agencies to connect OpenEMIS with other government information system and to develop new tools operating with OpenEMIS | • QRC to identify trainees • Trainees should be software developers with general knowledge about information system interfacing using APIs | • QRC nominates relevant trainees • UNESCO/CSF delivers the training | • Number of staff trained • % of trainees who successfully passed skill evaluation at the end of the training | Not started | 2021-10-01 | 2021-11-01 | High | bar: Q4 2021 Oct M14 to Q4 2021 Nov M15
1.1.4b | QRC | Capacity Development | Data and information management | Implement one landing homepage (JoLearn) to host all MoE Systems (OpenEMIS, Darsak, NoorSpace) | this activity aims at establishing a new URL for JoLearn as the landing hompage for MoE systems | this activity will enable MoE staff to easily access key systems from a single landingpage | requirements specifications delivered by QRC | • QRC to coordinate with a 3rd party to implement the single landing page • QRC to provide the necessary requirements to the 3rd party • 3rd party to design and implement the single landing page | • JoLearn landing page is online and fucntioning as required | Ongoing | 2021-06-01 | 2021-09-01 | High | bar: Q2 2021 Jun M10 to Q3 2021 Sep M13
1.1.5 | MODEE | EMIS Feature Enhancement | Data and information management | Improvement of CSPD integration with OpenEMIS (2b-5) | The government recently released a new web service to connect with CSPD, named GSB Web Service. OpenEMIS should be able to use the realtime GSB Webservice for all CSPD verifications, instead of the current snapshot file stored in OpenEMIS Identity | UNESCO/CSF will provide technical guidance and backstopping to the MoE-QRC team to ensure proper planning and implementation for this activity, including building the capacity of the relevant team in managing such exercise. This activity will reinforce synergies between MoE and MoDEE and further align MoE's EMIS with government ICT policies. | Activity 1.1.1 | • The Ministry of Digital Economy and Entrepreneurship has provided detail documentation on how to integrate OpenEMIS with CSPD via The GSB Web Service • The UNESCO/CSF reviews the GSB Web Service documentation and reverts with any questions • The UNESCO/CSF works closely with The MoE to come up with a plan to make the required changes in OpenEMIS to connect to the GSB Web Service rather than OpenEMIS Identity for details on new students/staff. | GSB Web Service is used in all OpenEMIS processes requiring CSPD data | Not started | 2022-02-01 | 2022-05-01 | Medium | bar: Q1 2022 Feb M18 to Q2 2022 MayM21
1.1.6 | QRC | Capacity Development | Data and information management | Training on Oracle Linux system administration, including on VmWare Manager and Monitoring and MySQL backup tools for QRC System administration team (2b-8) | A number of IT systems underneath are required for OpenEMIS operations in MOE. The MOE does not have enough knowledge to manage these systems | The QRC team is not yet capable of fully administering EMIS server operating systems, leading to high dependency to an external service provider. This training proposes to address this gap. This capacity development activity complements Activity 1.1.2 | Activity 1.1.1 | • QRC nominates relevant trainees • UNESCO supports the delivery of the training through a certified VMWare and MySQL training organization | % of trainees successfully passing end of training evaluations Post training assessment results to prove improved capacity of QRC technical team | Not started | 2022-02-01 | 2022-03-01 | Medium | bar: Q1 2022 Feb M18 to Q1 2022 Mar M19
1.1.7 | QRC | EMIS Feature Enhancement | Data and information management | Migration of OpenEMIS on a sustainable and robust hosting solution (1b-2) | The current EMIS applications are hosted on local hardware managed by QRC. As a consequence, MOE has to maintain very large hardware infrastructures which are underutilized most of the time and saturated during peak data entry periods (mark data entry). The MOE should explore more cost effective and sustainable hosting options such as scalable cloud hosting on government cloud or major cloud service providers (Amazon AWS or Microsoft Azure). Hosting the EMIS on the cloud would enable MOE to use the EMIS like a Software as a Service (SaS), avoiding for costly hardware maintenance and replacement. The activity includes an initial hardware procurement cost estimate for the project period, which will be tuned based on the results of the cost/benefit analysis for EMIS hosting. | UNESCO/CSF will provide technical guidance and backstopping to the MoE-QRC team to ensure proper planning and implementation for this activity, including building the capacity of the relevant team in managing such exercise. | NA | • UNESCO/CSF to provide the technical backstopping to MoE/QRC to conduct a cost/benefit analysis of cloud hosting versus local hosting on short term (2y) and long term (10y) • MoE/QRC makes a decision on the optimal hosting option based on the outcomes of the analysis and with technical backstopping provided by UNESCO/CSF • UNESCO will provide technical support to the MoE to ensure that OpenEMIS hardware and infrastructure are adequate to support OpenEMIS operations | cost/benefit analysis on EMIS hosting options available and endorsed by MOE | Ongoing | 2020-09-01 | 2022-01-01 | High | bar: Q3 2020 Sep M1 to Q1 2022 Jan M17
1.1.8 | QRC | EMIS Feature Enhancement | Data and information management | Integration of student marks from MoE LMS Platform into OpenEMIS | The MOE willing to scale up use of one LMS solution. This activity proposes to develop an API or an Import function in OpenEMIS Core, to enable OpenEMIS to easily retrieve and store student marks from the LMS Platform. LMS application, integration with OpenEMIS would ease the recording of student marks into OpenEMIS and reduce the load on teachers for student mark data entry | In addition to the technical support provided by UNESCO/CSF to implement the required integration, the capacity of the MoE/QRC team will be further strengthened in implementing requested API integration with OpenEMIS | Activity 1.1.1 | • MOE conducts a cost/benefit analysis about LMS solutions integration into OpenEMIS with UNESCO/CSF's technical advice • UNESCO/CSF provides realistic technical options for integration • MOE elaborates a realistic plan for LMS integration based on UNESCO/CSF recommendations • UNESCO/CSF provides technical assistance services to develop the API/Import features into OpenEMIS • LMS technology provider eventually adapt LMS to match with the requirements of the integration plan • UNESCO/CSF trains MOE focal points on the procedure for importing LMS Marks into OpenEMIS | • Availability of a cost/benefit analysis on LMS integration • Availability of a LMS Integration Plan • LMS Integration features working as per LMS Integration Plan | Ongoing | 2021-03-01 | 2021-09-01 | High | bar: Q1 2021 Mar M7 to Q3 2021 Sep M13
1.1.9 | QRC | EMIS Feature Enhancement | Data and information management | Full integration of MoE LMS Platform into OpenEMIS | This activity proposes to develop an API in OpenEMIS Core, to enable OpenEMIS to easily exchange information between OpenEMIS and the LMS Platform. | In addition to the technical support provided by UNESCO/CSF to implement the required integration, the capacity of the MoE/QRC team will be further strengthened in implementing requested API integration with OpenEMIS | Activity 1.1.1 LMS Technology provider to provide integration requirements | • UNESCO/CSF provides technical assistance services to develop the API to exchange data between OpenEMIS and LMS. • LMS technology provider eventually adapt LMS to match with the requirements of the integration plan • UNESCO/CSF trains MOE focal points on the procedure for importing LMS Marks into OpenEMIS | data exchange between OpenEMIS and LMS is fully operational | Not started | 2021-07-01 | 2021-11-01 | High | bar: Q3 2021 Jul M11 to Q4 2021 Nov M15
Output 1.2: Improved EMIS System Coverage
1.2.1 | QRC | Capacity Development | Data and information management | Strengthening of Capacities for management of software development processes targeting QRC System Development Team (2c-2) | QRC System Development Team needs to be able to professionally manage and monitor EMIS software development processes, through formulation of software requirements, validation of wireframes and approval/deployment of software enhancements on EMIS PROD environment. This also entails the support to the MoE QRC team to translate MoE EMIS users' requirements into technical and functional specifications including taking part in the validation of their implementation. | This activity provides on the job capacity building to QRC team on managing the software development process by jointly performing the required steps for the Not started OpenEMIS development procedure. | • QRC System Development Team members identified | • UNESCO/CSF proposes and implements on the job capacity building through the entire OpenEMIS software development process. | • % of software enhancements managed by QRC through agreed process | Ongoing | 2020-09-01 | 2023-02-01 | Medium | bar: Q3 2020 Sep M1 to Q1 2023 Feb M30
1.2.2 | QRC | EMIS Feature Enhancement | Data and information management | Provision of software development services to improve OpenEMIS data capture and workflow features as per MoE's requirements (see below sub-tasks for details) (2c-1) | Below Sub-Tasks to be prioritized by the EMIS Technical Committee and then implemented by UNESCO/CSF into OpenEMIS: | This activity puts into practice the knowledge acquired under the previous training (Activity 1.2.1) for the entire duration of the programme. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. | Activity 1.2.1 | • EMIS Technical Committee reviews and prioritize requests • UNESCO/CSF jointly with QRC to translate requirements into technical and functional specifications • UNESCO/CSF proposes implementation scenario for each software requirement • EMIS Technical Committee approves the proposed scenario for each requirement • UNESCO/CSF implements the requirement in OpenEMIS as per agreed scenario • EMIS Technical Committee confirms that the requested feature was implemented as per agreed scenario | • % of requests implemented and deployed as per agreed software development scenario | Ongoing | 2020-09-01 | 2023-02-01 | High | bar: Q3 2020 Sep M1 to Q1 2023 Feb M30
|  |  | No. | SUB-TASKS OF 1.2.2 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Implement a workflow for approving the marks | When a teacher fills all his/her subject marks at end of semester. Teacher should send to homeroom teacher, then to school principal, then to field directorate. Marks should be locked. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2021-09-01 | 2022-02-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Feb M18
|  |  | 2 | Develop an import feature for importing the student marks on the assessments from Excel | The mark data entry template should be downloadable as and Excel file to be filled offline, and then imported back. MoE should be able to activate/disactivate it in the security module | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 3 | Develop an optional "catch-up" exam session | In the Jordanian education system, the student will not be considered as "fail" in exam unless he failed in four subjects, so if the student has failed in three subjects or less there will be a catch-up exam. QRC wants an enhancement in OpenEMIS Core to enter those optional catch-up exams marks if the student failed in 3 subjects or less. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-03-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Mar M19
|  |  | 4 | Develop a pass/fail option linked to the student promotion module | QRC wants to develop an enhancement on the Final Result feature for students after filling all marks. The final result will be a dropdown list and its options will be (Pass, Fail). This result should be displayed in the Student Assessment Report. If the students result is Fail then the student could not be promoted to the next grade. QRC wants to have a condition where promotion can only happen if marks are passed. This could be achieved with a “passed/failed” dropdown on exam result. Only passed could be promoted. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-02-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Feb M18
|  |  | 5 | Prevent Homeroom teacher role from editing and modifying subject marks entered by subject teachers | Currently, the homeroom teacher can edit all marks of his/her student, even when he/she is removed from the role authorized to edit subject marks. He/she should be only authorized to edit the marks of the subjects he is teaching. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-02-01 | 2021-09-01 | High | bar: Q1 2021 Feb M6 to Q3 2021 Sep M13
|  |  | 6 | Enhancement of the Core survey module: survey geographical coverage feature | Provide an enhancement to the survey module enabling to build and administer Administrative area specific questionnaires. Ex: If a field directorate creates a survey, survey should be sent only to schools/teachers/students within their area. Not just to specific Administrative area but also to Specific schools | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2021-10-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Oct M14
|  |  | 7 | Enhancement of the Core survey module: survey staff coverage feature | Provide an enhancement to the survey module enabling to build and administer a Staff survey that is targeting specific user roles and positions. Ex: If a field directorate creates a survey for school principals, the survey should be sent only to school principals. Ideally, when a survey is designed for teachers, it would be great if the survey can be targeted to a specific set of subject teachers (ex: survey for math teachers) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-09-01 | Medium | bar: Q3 2021 Sep M13 to Q3 2022 Sep M25
|  |  | 8 | Enhancement of the Core survey module: survey school coverage feature | The institution surveys should be only sent to "active" institutions | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-05-01 | bar: Q2 2021 MayM9
|  |  | 9 | Enhancement of the Core survey report module: Slider question type | Adding a new question type "Slider" to the list of questions offered in a survey | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2022-09-01 | 2022-11-01 | Low | bar: Q3 2022 Sep M25 to Q4 2022 Nov M27
|  |  | 10 | Enhancement of the Core survey module: Survey for Professional Development Trainees | Add a new type of surveys targeting PD trainees. Users should have the ability to send to survey to trainees of a specific set of training sessions. Since trainees may not be part of an institution, it is suggested that the STAFF and STUDENT Survey forms to fill are displayed under the user PROFILE | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2022-09-01 | 2022-11-01 | Low | bar: Q3 2022 Sep M25 to Q4 2022 Nov M27
|  |  | 11 | Improve readability of the student status in the current year | Promotion/repetition of students is logically stored in the previous year's records of a student (PROMOTED/REPEATED), while all students are registered as ENROLLED in current year. It is requested to ease identification of the student status by displaying on screen the following info: ENROLLED (AS REPEATER) or ENROLLED | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-02-01 | bar: Q1 2021 Feb M6
|  |  | 12 | Improve management of student nationalities | • In Field Options > Nationalities add a check box to make an Identity Type mandatory for a given nationality, so the user can’t enter any other identity type except the one that was chosen in the field options. • In Student=> General=> identity, we should not be able to change the default Identity type that is setup based on the nationality in the system configuration. • On the student overview page, we should show the default identity (has done currently), but also list other identities that were captured. • After adding a non-Jordanian student , if the user wants to change the nationality to Jordanian, he should get the info from the external data source, otherwise, change should not be accepted. • Whenever a nationality is changed, the corresponding ID number requirements should be requested and checked. • Avoid duplicate identity numbers | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-02-01 | bar: Q1 2021 Feb M6
|  |  | 13 | Enhancement of the OpenEMIS mapping features | • Provide a feature on the Institution Overview page to open the institution location in Google Maps website • Provide a field option to decide if latitude/longitude are mandatory fields or not • Provide a field option to set min and max values for latitude and longitude • Provide a field option to set and force the length of latitude and longitude values (number of decimals) • Provide a security feature enabling to select roles authorizes to enter/modify school coordinates. In Jordan school coordinates should not be editable by schools, while other fields on the Institution profile should remain editable. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-02-01 | bar: Q1 2021 Feb M6
|  |  | 14 | Improvement of the "Undo" operations linked to the basic student workflow procedures | • All the Undo operations (Repeated, Promoted, Transferred, and Withdrawn) should be located in one place, even though if there are a workflow for it (current undo operations on different pages (transfer records notably). MOE wants one page with all operations accessible) • Undo operations should trigger cascade updates on records: example of a BUG: a student is enrolled, then withdrawn. Then you enroll the student again by “adding it” to the school. Till now the logic is ok. However, if you UNDO the withdraw record THEN you END UP with duplicate enrollment record. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 15 | Add an option to modifying the student grade and specialty. | Add an option to modify the student grade and specialty: create a BYPASS function/feature allow admins to easily make changes of student grades. The bypass function should automatically ensure coherence of existing records linked to the change (promotion/repetition/transfer) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-03-01 | 2021-09-01 | High | bar: Q1 2021 Mar M7 to Q3 2021 Sep M13
|  |  | 16 | Record validation when adding guardians | Adding any type of user should optionally requires a check from an external data source first (especially the Guardians). This enhancement should be implemented on both Institutions and Directory pages: • This should be a configuration option. • The check on external source should also apply to the Directory (at least their should be feature to enable/disable this option) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2020-09-01 | 2021-09-01 | High | bar: Q3 2020 Sep M1 to Q3 2021 Sep M13
|  |  | 17 | CSPD Integration (Nationality and Names) | • When adding a user from external data source (currently CSPD) not all the external user records are Jordanian in the external source data, so the Nationality should be retrieved as well from external database (TO BE SOLVED BY USE OF MoDE CSPD API?) • When adding a student from external data source it should also import the Mother name and the Mother Nationality if exist. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2020-09-01 | 2021-09-01 | High | bar: Q3 2020 Sep M1 to Q3 2021 Sep M13
|  |  | 18 | Data Archiving feature in OpenEMIS Core | • Develop a feature to enable archiving of previous year’s data to reduce the OpenEMIS Core database size (especially the Assessments (marks) tables) • MongoDB could eventually be used as a separate document oriented DB containing archived data for schools, students and staff. Archived data should still be accessible in the OE UI, but read only (at least summary info about previous year records) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2020-12-01 | 2021-09-01 | High | bar: Q4 2020 Dec M4 to Q3 2021 Sep M13
|  |  | 19 | Enable Guardians to access their pupil's records | The guardians should be able to check their children’s information and assessments, bearing in mind that the guardian might be also a staff. While the feature is there, when guardian is added, his corresponding role is not updated, thus they don’t have access to their student info (BUG?) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-01-01 | bar: Q1 2021 Jan M5
|  |  | 20 | Enhancement of drop-out/withdraw functions | Provide a better way to identify the Drop Out students based on the absence days. • WITHDRAW+DROPOUT reason should be linked to number of absences days. When the student is absent for more x days, the student record should automatically change to WITHDRAW+DROPOUT • Have a report showing all withdrawn students by status/reason | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 21 | Enhancement of student transfer function | While the current transfer function allows Sending Institution to do a bulk transfer of students, the Receiving school(s) need to process student pending admission one by one. A feature should be developed to bulk accept pending admissions | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 22 | List page improvements - academic year filter | Add an academic year filter on the pages: o Institutions > Attendance > Students > Absence tab o Institutions > Attendance > Staff > Absence tab o Institutions > Students > Academic > Absences o Institutions > Staff > Career > Absences o Institutions > Staff > Career > Classes o Institutions > Staff > Career > Subjects | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-07-01 | Medium | bar: Q3 2021 Sep M13 to Q3 2022 Jul M23
|  |  | 23 | Student transfer from one field of study to the other | In the secondary education level, QRC needs a way to easily transfer the students between streams (fields of studies), for example to transfer student from the 11th scientific grade to 11th literary grade. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-03-01 | 2021-09-01 | High | bar: Q1 2021 Mar M7 to Q3 2021 Sep M13
|  |  | 24 | Infrastructure module - delete function | Enable ability to delete any of the infrastructures: in case on mistake of data entry, we should be able to DELETE the record instead of entering a close date | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-06-01 | Medium | bar: Q3 2021 Sep M13 to Q2 2022 Jun M22
|  |  | 25 | Infrastructure module - BUG | Because of custom fields created on old version of the DB, the view/edit pages on infrastructures creates an error message | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-01-01 | bar: Q1 2021 Jan M5
|  |  | 26 | Student Special Needs module | • The difficulty should be related to the Special Needs Type, every special need type has a different difficulty (what about special educational needs, other kind of barriers?) • Add a field (dropdown list) for Auxiliary devices • Add a field (dropdown list) for Supporting Institution, and if the user chooses the option "Other", a text field (Mention It) should be activated • Add a field (dropdown list) for Treatment Services. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2021-12-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 27 | Student Special Needs module | Develop custom reports for the special needs module, listing same info as for the Student and Staff reports but for only listing Special Needs students and staff. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 28 | Student learning outcomes rubrics | Enhance the Rubric module as agreed on wireframes dated 31st August 2016 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-10-01 | Low | bar: Q3 2021 Sep M13 to Q4 2022 Oct M26
|  |  | 29 | Integration of the Non-Formal subsector into Core | Propose a solution to register Non-formal education providers, learners and trainers | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2021-08-01 | 2021-10-01 | High | bar: Q3 2021 Aug M12 to Q4 2021 Oct M14
|  |  | 30 | Education System setup | • In the Administration > Education Structure > Grade Subjects, link the Grade Subjects to an academic year so that list of subjects for each grade can be updated every year based on revision of the curriculum. • Or, add option to subjects: visible/not visible for current year. If not visible, the subject should not appear on any screen in current year | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-02-01 | bar: Q1 2021 Feb M6
|  |  | 31 | Improvement of School Shift functions | Provide a feature enabling transfer of a shift (any shift, including first) and its data into a new single shift school | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2021-07-01 | 2021-09-01 | High | bar: Q3 2021 Jul M11 to Q3 2021 Sep M13
|  |  | 32 | Improvement of the school closing process | When closing an institution the system should: • Set all the infrastructure to (End of use) - clear • Transfer all the staff or end the assignment of the staff - clear •Transfer all the students or drop them out – clear •Close all the surveys automatically. •The system will view all the Workbench requests •If the school is a double shift school, then the remaining school shift type should set to “Single Shift Owner” • The school closure process could be ideally handled by a dedicated module where admin needs to perform all required steps one after the other | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-02-01 | bar: Q1 2021 Feb M6
|  |  | 33 | Improvement student overview page | The identity no. and type should be reflected on the student/teacher Overview page regardless of what it is defined on the Field Options > Nationalities | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-01-01 | bar: Q1 2021 Jan M5
|  |  | 34 | Enable non-academic institutions to record infrastructures | Infrastructure records being linked to shift information, it's not currently possible for non-academic institutions to record their infrastructure (no access to the shift module). One way to solve this, is by creating a default shift automatically in non-academic institutions (and maybe in all institutions at creation time). | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2021-12-01 | Meduim | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 35 | Improvement of the Calendar feature | Provide a way to attach some calendar events to users in schools offering specific grades. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-09-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Sep M25
|  |  | 36 | Enhancement of the usability of Admin=>Security=>Users | QRC wants Admin=>Security=> User page to behave like the Directory, where no record is displayed before you search/filter for something. This is because the Admin=>Security=> User is currently unusable due to the high number of records retrieved | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-11-01 | Low | bar: Q3 2021 Sep M13 to Q4 2022 Nov M27
|  |  | 37 | Enhancement of the Notices module | In Administration > System Setup > Notices, provide features to improve Notices: • Rich text, pictures and attachments (as in Wordpress or equivalent CMS) • Ability to reorder the notes. • Sending notices to specific roles | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-06-01 | Meduim | bar: Q3 2021 Sep M13 to Q2 2022 Jun M22
|  |  | 38 | Enhancement of Translations | Ensure that all UI text/messages that are still in English can be translated in Administration > Localization > Translation. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2021-05-01 | 2021-09-01 | High | bar: Q2 2021 MayM9 to Q3 2021 Sep M13
|  |  | 39 | Fix a CSS issue in Assessment data entry page | Assessment data entry form in Arabic on Chrome have some issues with CSS, where column titles are displayed right to left while rows are displayed left to right (and scrolling is opposite) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-01-01 | bar: Q1 2021 Jan M5
|  |  | 40 | Enhancement of the readability of the Institution=>Positions page | On the list of positions, display the name of the staff who is attached to each position, if any. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-05-01 | bar: Q2 2021 MayM9
|  |  | 41 | Alert on Absenteeism | Provide a Trigger feature creating an alert for School Principal and Homeroom Teacher when a student is absent for more than X days. The alert should be displayed in the Workbench, as well as sent by email | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2021-12-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 42 | Improvement of the Workflow module | Currently, when sending workflow event to the next step, the user needs to select in a list of assignees that is not easy to filter, notably when higher level admin are part of the workflow. The list should first display the users that are in the first educ/admin level above/below current user's level. The list should also display the role name of each assignee | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-07-01 | 2021-09-01 | High | bar: Q3 2021 Jul M11 to Q3 2021 Sep M13
|  |  | 43 | Improvement of the Workbench functions | Provide a way to search/filter Workbench records | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-07-01 | bar: Q3 2021 Jul M11
|  |  | 44 | Improvement of the Institution>Students>Withdrawn | Enable the search/filter option on Institution>Students>Withdrawn (not currently working) | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-01-01 | bar: Q1 2021 Jan M5
|  |  | 45 | Improvement of the Institution > Attendance > Staff > Absences page | Provide the ability to record a future date, for example if we need to enter a maternity leave before the leave starts. Currently, we can only record maternity leaves after the leave has ended, which is not right. Maternity leaves should be entered before the leave starts. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 46 | Develop the API features requested by Ministry of Digital Economy | Enhance OpenEMIS APIs to provide features required under activity 1.8 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2020-12-01 | bar: Q4 2020 Dec M4
|  |  | 47 | Daily recording of Meal distribution to students | Add a feature enabling daily recording of meals given to students at the time of daily student absence recording | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-02-01 | 2021-09-01 | High | bar: Q1 2021 Feb M6 to Q3 2021 Sep M13
|  |  | 48 | Add an export button on the Student > Academic > Assessments page | Provide an "export to Excel" feature on this page | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 49 | Enhancement of the Core survey report module | The survey report module should provide a feature enabling to only generate report for active schools | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Resolved/Endorsed |  | 2021-01-01 | bar: Q1 2021 Jan M5
|  |  | 50 | Infrastructure module - Export | Add an export option for the Infrastructure > Overview, which will export all the levels in the infrastructure. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-07-01 | 2021-09-01 | High | bar: Q3 2021 Jul M11 to Q3 2021 Sep M13
|  |  | 51 | Improvement of the Professional Development Training Module interface | • In Administration => Training=> sessions/results (not courses) filter records based on the security_user group. • Provide staff the ability to see their training records, as well as the ability to request a training/course directly from their profile page in Profile > Staff > Training. Fore the later, the training/course page should allow the user to either (1) enter a non-existing course (2) also enter an accredited courses if some are defined in the system • Create a feature to enable import of Training results in Administration > Training > Results In Administration > Training > Results & Administration > Training > Sessions pages, add a filter for records by FDs and training dates. • On Administration > Training > Courses > Add page, add a new field "Course category" (Central, Non - Central). the course category should be also visible in corresponding reports On Administration > Training > Results page, add a field "Attendance Days", and also add this field to the corresponding reports. • In Administration > Training > Results page put the different results on the same table or page, without relying on a dropdown list. • On the result page (Administration > Training > Results) add a field "Certificate Number", and add it to the corresponding report. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Under Development with OE Lab | 2021-06-01 | 2021-10-01 | High | bar: Q2 2021 Jun M10 to Q4 2021 Oct M14
|  |  | 52 | Enable Changes in the Education Structure across school years | • In Administration => Education Structure, each education structures to academic periods and enable copy of an education structure (including subjects) from one school year to the other. This is to avoid displaying subject in a school year that are no more teacher. | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 | Awaiting MoE | 2021-02-01 | 2021-09-01 | High | bar: Q1 2021 Feb M6 to Q3 2021 Sep M13
|  |  | 53 | Limit the maximum number of teaching hours for staff based on the max teaching hours defined in grade-subject | The maximum number of teaching hours for a staff should not exceed the official number of required hours assigned to the subject(s) thought by the teacher | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 54 | Update Administrative Boundaries to add Village and Neighborhood levels | List of Villages and neighborhoods are required by the Building and Infrastructure Division | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2021-12-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 55 | Enabling students to emit wishes for next school year education programme and school | When more than one programme is offered after completion of an education programme, provide an option enabling students to emit a wish on the programme they would like to go to after promotion. Link this feature with reports on wishes and workflows for approval/rejection Automating the tenth-grade student distribution plan for secondary vocational education branches and coordinating annually with the Vocational Education Department in determining the capacity for vocational education workshops for all vocational disciplines to determine the increment size of vocational workshops NEW MODULE FOR STUDENT EXPRESSION OF INTEREST FOR PROMOTION | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-03-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Mar M19
|  |  | 56 | Customization of the Workflow Engine for HR management requirements | Enable addition of custom fields to each workflow step | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | See Activity 1.2.2 |  | 2021-09-01 | 2022-02-01 | bar: Q3 2021 Sep M13 to Q1 2022 Feb M18
|  |  | 57 | Improvement of OpenEMIS Staff Mobile Application | enhancement to the Staff Mobile App to better align with OpenEMIS Staff module | Same as Activity 1.2.2 | same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 58 | Improvement of OpenEMIS Survey Mobile Application | enhancement to the Staff Mobile App to better align with OpenEMIS Survey module | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 59 | Improvement of OpenEMIS Classroom Mobile Application | enhancement to the Staff Mobile App to better align with OpenEMIS Classroom module | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 60 | Improvement of Custom Fields to link to providers | Improvement of Custom Fields to link to one or all providers | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 | Same as Activity 1.2.2 |  | 2022-10-01 | 2022-12-01 | Low | bar: Q4 2022 Oct M26 to Q4 2022 Dec M28
1.2.3 | QRC | Capacity Development | Data and information management | Development or update of OpenEMIS training materials to reflect software enhancements done under activity 1.2.2 (2c-3) | This activity will ensure that all changes/improvements made to OpenEMIS software are documented in the online OpenEMIS Knowledge Base in Arabic. A hard copy snapshot of the knowledge base will be also provided to MOE | MOE should reflect the online knowledge base into localized training materials for target users, with the support provided by UNESCO in assuring the production of clear and High quality OpenEMIS training materials. This activity will entail strengthened capacity of the QRC quality assurance team in validation and auditing of the OpenEMIS training content. | QRC EMIS Quality Assurance team members identified | • UNESCO/CSF develops generic training material for each feature implemented under activity 1.2.2 and to upload them on the global OpenEMIS Knowledge Base (https://support.openemis.org/core/en/home-en/) • QRC translates materials in Arabic and update if necessary to embed them into Jordanian EMIS training materials with the support provided by UNESCO on the quality assurance aspect of the training materials. | • % of features documented in the OpenEMIS knowledge base • % of features documented in MOE Arabic training materials • No. of user manuals prepared and updated (user manual per each MoE administrative level) = 3 • No. of trainer manuals prepared and updated (trainer manual per each MoE administrative level) = 3 | Not started | 2021-09-01 | 2023-01-01 | Medium | bar: Q3 2021 Sep M13 to Q2 2022 Jun M22
1.2.4 | QRC | Capacity Development | Data and information management | Provision of local technical support on use of OpenEMIS features (2c-4) | Two Arabic speaking EMIS experts will be hired by UNESCO/CSF and deployed full-time on-site in QRC and Planning. They will be providing daily assistance and capacity building services to MOE for all aspects related to use and management of OpenEMIS and help building synergies between QRC and other departments of the MOE, such as the Planning and Research Dept. | The deployment of two local OpenEMIS experts on-site will assist MOE stakeholders in the implementation of all activities listed in the operational plan. This team will notably ease communications between all the programme stakeholders | NA | • UNESCO/CSF develops terms of refence for the two local experts • UNESCO/CSF hires and deploy two local experts • MOE provides an office space for the two experts in QRC and Planning Department | • Number of person/day local support provided within the programme period | Ongoing | 2021-01-01 | 2023-02-01 | High | bar: Q1 2021 Jan M5 to Q1 2023 Feb M30
1.2.5 | QRC | Capacity Development | Data and information management | Provision of help Desk and technical support (30 Months) (2c-5) | This activity will provide 2 years access to the global OpenEMIS help desk and maintenance service. The Help Desk and Maintenance service provides 24 hour / 7-day remote technical Help Desk for troubleshooting and assistance. This activity also includes the regular provision of software updates and patches to ensure the OpenEMIS architecture used in Jordan is up to date with the latest fixes and features released by the global OpenEMIS Initiative | This service will enable QRC to get timely technical assistance and advice from global OpenEMIS Lab experts during the entire duration of the SSP programme. | Activity 1.2.1 | • UNESCO/CSF opens an OpenEMIS Service Desk environment for MOE • MOE/QRC identifies focal point for interaction with Service Desk • MOE/QRC submits Service Desk requests as per guidelines provided under activity 1.2.1 • UNESCO/CSF processes the requests and provides the necessary support (except for requests for new features in OpenEMIS) • UNESCO/CSF will provide the necessary capacity building to MoE to fully utilize this global OpenEMIS help desk system | • Number of Service Desk requests submitted during the programme • % of Service Desk tickets resolved | Ongoing | 2020-09-01 | 2023-02-01 | Critical | bar: Q3 2020 Sep M1 to Q1 2023 Feb M30
1.2.6 | Directorate of Policy and Strategic Planning | EMIS Feature Enhancement | Data and information management | Configuration & software development of the existing OpenEMIS modules to capture new data requirements of the Strategic Policies and Planning Directorate. (2c-1) | This activity aims at analysing the options to configure or develop OpenEMIS Core modules in order to enable the Directorate of Policy and Strategic Planning to collect relevant data through OpenEMIS. | This activity and related sub-activities will enable the Directorate of Policy and Strategic Planning to get more benefits from OpenEMIS datasets, in relation to their data needs. | Activity 1.2.1 | • MOE/QRC identifies focal point for identifying data requirements from target Directorate • MOE/QRC proposes solutions to capture the data requirements in OpenEMIS Core using existing features (Surveys, custom fields, field options), and when feasible and within the scope of EMIS • UNESCO/CSF advices MOE/QRC on recommended approach for data capture • MOE/QRC implements the changes in OpenEMIS Core and report back the target Directorate | • Report on OpenEMIS Core customizations made for the target Directorate | Ongoing | 2021-04-01 | 2022-04-01 | High | bar: Q4 2020 Dec M4 to Q2 2022 Apr M20
1.2.6.1 | Directorate of Policy and Strategic Planning | EMIS Feature Enhancement | Data and information management | Configuration of existing OpenEMIS modules to capture new data requirements of the Strategic Policies and Planning Directorate | This activity aims at further tuning the configuration of existing OpenEMIS Core modules in order to enable the Directorate of Policy and Strategic Planning to collect relevant data through OpenEMIS. Analysis of Sub-Activities was performed under activity 1.2.6 | QRC will lead in configuration of OE modules with technical backstopping and support from UNESCO/CSF | Activity 1.1.1 | • Directorate of Policy and Strategic Planning to provide specifications and to review and endorse • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required | • Report on OpenEMIS Core configurations made for the target Directorate | Ongoing | 2021-07-01 | 2021-11-01 | Medium | bar: Q3 2021 Jul M11 to Q4 2021 Nov M15
|  |  | No. | SUB-TASKS OF 1.2.6.1 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | EMIS Gender Section - Data of gifted students and of King Abdullah Schools of Excellence Special need module + KBSE on general overview as a custom field | adding a cutom field to identify All King Abdullah Schools of Excellence and they can find all data related to them through filtering by their institution's name | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | completed | 2021-07-01 | 2021-07-01 | Medium | bar: Q3 2021 Jul M11
|  |  | 2 | Educational Statistics Division - Number of teachers, by gender and years of service | QRC to discuss further with HR | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 3 | Educational Statistics Division - Data of teachers of the international system | QRC will add New education system | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 4 | Educational Statistics Division - Numbers of special education schools | QRC added a custom field on the institution overview page to identify those schools | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 5 | Educational Statistics Division - Numbers of literacy centers with the numbers of individuals enrolled | QRC will add New Literacy centers | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 6 | Educational Statistics Division - Data regarding schools teaching the international system | QRC will add it as a new programme | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 7 | School Map Department - Teachers and detective form requested by the Pakistani expert for use through the webgis system | Department staff asked for login ID, QRC team will configure an account on OpenEMIS for all school Map department staff | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 8 | Policy and Strategic Planning - Identify schools that suffer from student overcrowding and indicate the size of overcrowding | According to previous report QRC can identify overcrowded schools | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Aug M12 to Q4 2021 Nov M15
1.2.6.2 | Directorate of Policy and Strategic Planning | EMIS Feature Enhancement | Data and information management | Software Development to enhance existing OpenEMIS modules to capture new data requirements of the Strategic Policies and Planning Directorate | This activity aims at further development of existing OpenEMIS Core modules in order to enable the Directorate of Policy and Strategic Planning to collect relevant data through OpenEMIS. Analysis of Sub-Activities was performed under activity 1.2.6 | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. | Requirement Specifications to be provided by the Directorate of Policy and Strategic Planning | refer to Roles and Responsibilities defined in Software Development SOPs | percentage of requests implemented and deployed as per agreed software development scenario | Not started | 2021-08-01 | 2022-04-01 | High | bar: Q3 2021 Aug M12 to Q2 2022 Apr M20
|  |  | No. | SUB-TASKS OF 1.2.6.2 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | EMIS Gender Section - Leadership and supervisory centers data on human resources, by gender | CSF will add a new category to staff positions so that we can generate a report regarding leadership and supervisory positions. | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2021-12-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 2 | EMIS Gender Section - Number of participants in extra-curricular activities such as fingerprint and fitness | Development of a new report | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 3 | Educational Statistics Division - Number of school principals by gender | the report already exist in the system (custom report No. 19), needs enhancement | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2021-12-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 4 | Educational Statistics Division - Number of teachers in special education schools | Development of a new report | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2021-10-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Oct M14
|  |  | 5 | Educational Statistics Division - Number of students in the international system, by gender and grade | Development of a new report | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2021-12-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
|  |  | 6 | Educational Statistics Division - The numbers of joined sections in schools (multi-grade classes) | the report already exist in the system (custom report No. 10), needs enhancement ( covered under activity 1.3.4 sub activity 18 ) | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 7 | Educational Statistics Division - Numbers of schools that use the Smart board | Development of a new report | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2022-05-01 | Medium | bar: Q3 2021 Sep M13 to Q2 2022 MayM21
|  |  | 8 | Educational Statistics Division - Numbers of connected schools on the internet | Development of a new report | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 9 | Educational Statistics Division - Comprehensive and specialized vocational schools ADD A MEAN TO MORE EASILY IDENTIFY THE VOC SCHOOLS and build a report by education programme (active/inactive) | improve the institution advanced search capability | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2022-02-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Feb M18
|  |  | 10 | Policy and Strategic Planning - Determine the numbers of students who transfer from private schools to public schools and distribute them to all districts to indicate the number of those transferred and the size of pressure on public school facilities to determine the regional requirements of school buildings and additional classrooms | Development of a new report | Software Development SOP |  |  |  | Not started | 2021-09-01 | 2021-10-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Oct M14
|  |  | 11 | Educational Statistics Division - Data of all female schools | CSF will do it as configuration on database | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-08-01 | 2021-10-01 | High | bar: Q3 2021 Aug M12 to Q4 2021 Oct M14
|  |  | 12 | EMIS Gender Section - Ratios of scholarships by gender | QRC will add a custom field or will configure the Scholaship feature on the System CSF will develop a new report Just for staff | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 13 | EMIS Gender Section - Data on violence. | Development of a new report | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 14 | Formations Department - Number of teachers by rank | Development of a new report | refer to Activity 1.2.6.1 | Specifications and information linked to configuration to be requested from Directorate of Policy and Strategic Planning | refer to Activity 1.2.6.1 | official endoresment from Directorate of Policy and Strategic Planning | Not started | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
1.2.7 | Property Directorate | EMIS Feature Enhancement | Data and information management | Configuration & software development of the existing OpenEMIS modules to capture new data requirements of the Property Directorate (2c-1) | This activity aims at analyse the options to configure or develop OpenEMIS Core modules in order to enable the property directorate to collect relevant data through OpenEMIS. | This activity will enable the Property Directorate to get more benefits from OpenEMIS datasets, in relation to their data needs. | Activity 1.2.1 | • MOE/QRC identifies focal point for identifying data requirements from target Directorate • MOE/QRC proposes solutions to capture the data requirements in OpenEMIS Core using existing features (Surveys, custom fields, field options), and when feasible and within the scope of EMIS • UNESCO/CSF advices MOE/QRC on recommended approach for data capture • MOE/QRC implements the changes in OpenEMIS Core and report back the target Directorate | • Report on OpenEMIS Core customizations made for the target Directorate | Ongoing | 2021-04-01 | 2022-01-01 | High | bar: Q2 2021 Apr M8 to Q1 2022 Jan M17
1.2.7.1 | Property Directorate | EMIS Feature Enhancement | Data and information management | Configuration | This activity aims at further tuning the configuration of existing OpenEMIS Core modules in order to enable the property directorate to collect relevant data through OpenEMIS. Refer to the final agreed table of requirements analysis as output of activity 1.2.7. | [5 empty] | 2021-09-01 | 2021-11-01 | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | No. | SUB-TASKS OF 1.2.7.1 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Create a account for Acquisition Department for using the EMIS system for easy access to information | QRC team will configure an account on OpenEMIS for all Acquisition department staff |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
1.2.7.2 | Property Directorate | EMIS Feature Enhancement | Data and information management | Software development | This activity aims at further enhance the existing OpenEMIS Core modules in order to o enable the property directorate to collect relevant data through OpenEMIS. Refer to the final agreed table of requirements analysis as output of activity 1.2.6. | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. |  | refer to Roles and Responsibilities defined in Software Development SOPs | percentage of requests implemented and deployed as per agreed software development scenario |  | 2021-09-01 | 2022-01-01 | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | No. | SUB-TASKS OF 1.2.7.2 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 2 | Rental and Investment Department - Link the national numbers of schools to the system of rented properties to come up with real statistics for the numbers of rented properties and annexes | Development of a new report | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-09-01 | Medium | bar: Q3 2021 Sep M13 to Q3 2022 Sep M25
1.2.8 | Educational Research and Development Directorate | EMIS Feature Enhancement | Data and information management | Configuration & software development of the existing OpenEMIS modules to capture new data requirements of the Educational Research and Development Directorate (2c-1) | This activity aims at further tuning the configuration of existing OpenEMIS Core modules in order to enable the Educational Research and Development Directorate to collect relevant data through OpenEMIS. | This activity will enable the Educational Research and Development Directorate to get more benefits from OpenEMIS datasets, in relation to their data needs. | Activity 1.2.1 | • MOE/QRC identifies focal point for identifying data requirements from target Directorate • MOE/QRC proposes solutions to capture the data requirements in OpenEMIS Core using existing features (Surveys, custom fields, field options), and when feasible and within the scope of EMIS • UNESCO/CSF advices MOE/QRC on recommended approach for data capture • MOE/QRC implements the changes in OpenEMIS Core and report back the target Directorate | • Report on OpenEMIS Core customizations made for the target Directorate | Ongoing | 2021-04-01 | 2021-11-01 | High | bar: Q2 2021 Apr M8 to Q4 2021 Nov M15
1.2.8.1 | Educational Research and Development Directorate | EMIS Feature Enhancement | Data and information management | Configuration | This activity aims at further tuning the configuration of existing OpenEMIS Core modules in order to enable the Educational Research and Development Directorate to collect relevant data through OpenEMIS. Refer to the final agreed table of requirements analysis as output of activity 1.2.6. | [5 empty] | 2021-09-01 | 2021-11-01 | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | No. | SUB-TASKS OF 1.2.8.1 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Educational Research Department - Grant the educational research department the authority to view all data on the OpenEMIS system as this this data is required for conducting studies | QRC team will configure an accounts on Open EMIS for all research department staff |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 2 | Educational Research Department - Ability to prepare and distribute research tools and monitor responses through the OpenEMIS system | QRC will configure Survey |  | sub-activity 1.2.2.6 sub-activity 1.2.2.7 | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 3 | Monitoring and Evaluation Department - First, all major and sub-indicators of the strategic plan are downloaded to the system and the system provides the ability for continuous update | QRC will use the OpenEMIS DataManager to download and update the indicators from strategic plan |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 4 | Monitoring and Evaluation Department - Second, indicators for the national strategy for human resources development should be downloaded and made available for updating | QRC will use the OpenEMIS DataManager to download and update the indicators national strategy |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 5 | Monitoring and Evaluation Department - Third, the system provides the ability to download and update achievements on a monthly basis | Planning Department will use the OpenEMIS Monitoring to download and update achievements |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 6 | Monitoring and Evaluation Department - Fourth, there should be ease of access in dealing with the system so update or extract of information could be done at all times without the need for official approval | QRC team will configure an accounts on Open EMIS for all M&E department staff |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 7 | Monitoring and Evaluation Department - Adding government work priorities and enabling the addition of achievements for each priority | Planning Department will use the OpenEMIS Monitoring to update adding government work priorities |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  |  | 2021-09-01 | 2021-11-01 | Medium | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
1.2.9 | Human Resources Directorate | EMIS Feature Enhancement | Data and information management | Configuration & software development of the existing OpenEMIS modules to capture new data requirements of the Human Resources Department (2c-1) | This activity aims at further tuning the configuration of existing OpenEMIS Core modules in order to enable the Human Resources Directorate to collect relevant data through OpenEMIS. | This activity will enable the Human Resources Directorate to get more benefits from OpenEMIS datasets, in relation to their data needs. | Activity 1.2.1 | • MOE/QRC identifies focal point for identifying data requirements from target Directorate • MOE/QRC proposes solutions to capture the data requirements in OpenEMIS Core using existing features (Surveys, custom fields, field options), and when feasible and within the scope of EMIS • UNESCO/CSF advices MOE/QRC on recommended approach for data capture • MOE/QRC implements the changes in OpenEMIS Core and report back the target Directorate | • Report on OpenEMIS Core customizations made for the target Directorate | Ongoing | 2021-04-01 | 2022-07-01 | bar: Q2 2021 Apr M8 to Q3 2022 Jul M23
1.2.9.1 | Human Resources Directorate | EMIS Feature Enhancement | Data and information management | Configuration | This activity aims at further tuning the configuration of existing OpenEMIS Core modules in order to enable the Human Resources Department to collect relevant data through OpenEMIS. Refer to the final agreed table of requirements analysis as output of activity 1.2.6. | [5 empty] | 2021-07-01 | 2021-07-01 | bar: Q3 2021 Jul M11
|  |  | No. | SUB-TASKS OF 1.2.9.1 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Employment and Staff Department - Heads of Department should have accounts on the system | QRC team will configure an accounts on Open EMIS for all Employment and staff department staff |  |  | • MoE/QRC to configure the requirements • UNESCO/CSF to provide technical backstopping as required |  | completed | 2021-07-01 | 2021-07-01 | bar: Q3 2021 Jul M11
1.2.9.2 | Human Resources Directorate | EMIS Feature Enhancement | Data and information management | Software development | This activity aims at further enhance the existing OpenEMIS Core modules in order to o enable the Human Resources Department to collect relevant data through OpenEMIS. Refer to the final agreed table of requirements analysis as output of activity 1.2.6. | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. |  | refer to Roles and Responsibilities defined in Software Development SOPs | percentage of requests implemented and deployed as per agreed software development scenario |  | 2021-09-01 | 2022-07-01 | bar: Q3 2021 Sep M13 to Q3 2022 Jul M23
|  |  | No. | SUB-TASKS OF 1.2.9.2 | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Employment and Staff Department - The system should calculate the technical status of each School in FDs based on the forms filled by the directorate on the technical status of schools The amendment is made to the technical status of each school after each transfer of employees, appointments through civil service bureau or overtime appointment (overtime appointment does not affect the technical status as vacancy is maintained), or dismissal from work | Development of a new report | Software Development SOP | Sub-activity 1.3.4.8 |  |  |  | 2021-09-01 | 2022-03-01 | High | bar: Q3 2021 Sep M13 to Q1 2022 Mar M19
|  |  | 2 | Develop a new workflow to assign staff to positions | Employment and Staff Department - Recruitment of new employees: The Ministry downloads the excel file from CSB, OR RETRIVE FROM CSB DB API DIRECTLY with the names of new employees with - National number - Full Name - The Directorate - Specialization and qualification - Place of residence - Comments "Employment and Staff Department - The Staff Department of the Directorate determines the employment positions for new employees whose names have been uploaded by the Ministry => Staff Department allocates new employee records to each FD => FDs eventually create positions and trigger workflow for staff assignment to position." Employment and Staff Department - The school principal approves the appointment once employee commences work. In the event of commencement, a direct letter of commencement is issued to the employee and a notice of commencement (with the commencement date added by the principal) is sent to the Ministry "Employment and Staff Department - In the event an employee declines work , there are two cases: - Declination before being distributed to schools, then it is rejected by the directorate - Declination after being distributed to schools and before commencement is rejected by the school" | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-09-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Sep M25
|  |  | 3 | Employment and Staff Department - Addition of a new option upon completing the appointment on the system, specifying the cause of termination of appointment (transfer, retirement, ...) End of assignment: add a field for reason | Add a "Reason" field to the end of assignment workflow | Software Development SOP |  |  |  |  | 2021-09-01 | 2021-10-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Oct M14
|  |  | 4 | Employment and Staff Department - Addition of new features for employees requests Request for external transfer: A staff transfer Workflow initiated by the staff who want to be transferred and going directly to central MOE. After approval by central MOE, FD assigns to a school - From the employee's account - Employee identifies two directorates (with the possibility of changing to other directorates) - Process flow chart (employee => Ministry) with the possibility of making amendments in the future - If approved, it should affect the technical status | Develop a workflow to allow staff to request transfer | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 5 | Employment and Staff Department - Request for internal transfer A staff transfer Workflow initiated by the staff, and staying within FD From the employee's account Employee identifies desired school to transfer to (with the possibility of changing to other schools) Process flow chart (employee => Directorate) with the possibility of making amendments in the future If approved, it should affect the technical status | Develop a workflow to allow staff to request transfer | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-08-01 | High | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 6 | Employment and Staff Department - Request for amendment of job title – Reason for requesting the amendment (new educational qualification, health status, others) Process flow chart (employee => Directorate => Ministry) Under approval for the amendments of job title, The Directorate’s computer screen contains two options: Agree, without replacement Agree, provided that a replacement is available (disagree) WORKFLOW ON STAFF RECORD UPDATES, INITIATED BY STAFF | Develop a workflow to allow staff to request to change position title | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-09-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Sep M25
|  |  | 7 | Employment and Staff Department - Request to change the job title to assistant principal or principal Submit the application from employee's account Process flow chart (employee => Directorate => Ministry) The directorate screen contains options for adding marks according to the specified categories, and the average score is calculated. Successful applications are submitted to the Ministry. | Develop a workflow to allow staff to request to change position title (only for assistant principal or principal) | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-09-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Sep M25
|  |  | 8 | Employment and Staff Department - WORKFLOW STEP REPORTS | Development of a new report report to be built on sub-activities 6 and 7 | Software Development SOP | Sub-activity 1.2.9.2.6 Sub-activity 1.2.9.2.7 |  |  |  | 2021-09-01 | 2022-10-01 | Low | bar: Q3 2021 Sep M13 to Q4 2022 Oct M26
|  |  | 9 | Staff Performance Review and Analysis Department - Addition of 13 performance forms to the system to be filled out (through surveys or customization of the staff performance module) Staff Performance Review and Analysis Department - Each employee is evaluated by their line manager Staff Performance Review and Analysis Department - Records are distributed electronically, by designated staff responsible for distributing forms in the directorate or the ministry’s center | Update the Staff Apprasial feature to link the staff apprasials forms to the 13 positions. A PDF document needs to be attached to the staff performance apprasial form such that it can be downloaded, filled and uploaded back to the staff performance apprasial form. The form will then be submitted to the workflow. Add a field to OpenEMIS Core Staff Positions called "Reports To" to establsih a reporting relationship between positions so we can calculate the "line manager" for the workflow. | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-10-01 | Low | bar: Q3 2021 Sep M13 to Q4 2022 Oct M26
|  |  | 10 | Information Department - Dismissal from work Termination Redundancy Other | Develop of a new Report linked to Sub-activity 1.2.9.2.3 | Software Development SOP |  |  |  |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2022 Nov M27
|  |  | 11 | Vacations Department - Requesting leave without pay Required information in the form: - National number - Ministerial Number - Full name - Phone number - Workplace - Leave period (from - to) - Cause of leave - Job title | Feature already exists in OpenEMIS Core. Add the option for staff to submit their own leave request from the Personal module | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-07-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Jul M23
|  |  | 12 | Vacations Department - In the event that the leave is extended (knowing that the employee has been dismissed and his affiliation with the directorate is terminated) there should remain a link between the employee and the directorate | Link the Staff Leave request to the school. | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-07-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Jul M23
|  |  | 13 | Vacations Department - Reports required - Report requests for leave according to case (open, pending approval or under study, disapproved) - Report of those whose leave is nearing completion | Development of a new report | Software Development SOP | Sub-activity 1.2.9.2.11 |  |  |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 14 | End of Service Department - Request for retirement at the request of the employee (early retirement / retirement) Required information: National ID number Ministerial Number Full name Phone number Workplace Job title (job position) Social status Number of children The name of spouse Current degree Date it became effective Process flow chart (Workflow) Employee => Directorate => End of Service Section => Payroll Department and Directorate | Feature already exists in OpenEMIS Core. Add the option for staff to request to end their assignment from the Personal module. | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-07-01 | Medium | bar: Q3 2021 Sep M13 to Q3 2022 Jul M23
|  |  | 15 | End of Service Department - Resignation: The information required is the same as the retirement information Process flow chart (Workflow) Employee => Directorate => Scholarships Department => Payroll Department => Directorate => End of Service Department => Payroll Department | Develop a new workflow in OpenEMIS Core to change employment status to "Resigned". | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-07-01 | Medium | bar: Q3 2021 Sep M13 to Q3 2022 Jul M23
|  |  | 16 | End of Service Department - Notice of suspension from work (in case of suspension from work for more than 10 days): The information required is the same as the retirement information Process flow chart (Workflow) Directorate => End of Service Department => Payroll Department=> End of Service Department => Directorate | Develop a new workflow in OpenEMIS Core to change employment status to "Suspended". A system configuration item may also be required to automatically trigger this workflow based on staff days absent. | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-08-01 | Low | bar: Q3 2021 Sep M13 to Q3 2022 Aug M24
|  |  | 17 | Bonus and Ranks Department - Request to add a qualification: Attach a certified educational qualification and certificate equivalency in the event of graduation from abroad or from the Arab Open University (compulsory) Attach the letter of approval to completion of studies Required information: - National ID number - Ministerial Number - Full name - Phone number - Workplace - ob title (job position) - Category - New qualification (Dropdown list) with the specialization code from the Information Department - Funding body ( Dropdown list) - Major specialization (Dropdown list) with the specialization code from the information department - Subspecialty - Drop Dropdown list with country code from information department - University name (Dropdown list) with the university code from the information department - Qualification date - Evaluation or grade Process flow chart (Workflow) -Employee => Directorate => Promotion Department - Report of the employees whose new qualifications are accepted by the end of the year for the bonuses and promotions section and the payroll department (preferably the report in CSV format) | Add workflow function to the existing staff qualifications feature. Add the option for staff to submit their qualification via the Personal module. | Software Development SOP |  |  |  |  | 2021-09-01 | 2022-10-01 | Low | bar: Q3 2021 Sep M13 to Q4 2022 Oct M26
Output 1.3: Improved EMIS Reporting and Dashboard Building Capacities
1.3.1 | QRC | Capacity Development | Monitoring and reporting | Training on OpenEMIS Data Architecture (2d-1) | This training is dedicated to the analysis of the database schemas used by OpenEMIS applications. It is especially designed for QRC database administrators who want to acquire a deep understanding of the data structures used by OpenEMIS to record EMIS information. | This training will explain to the QRC/EMIS System Administration team how information is stored and structured into the OpenEMIS Core database. Deep knowledge of the database structure is critical for QRC to develop reports by themselves. | Trainees should have a good understanding of relational database and Structured Query Language (SQL) | • QRC nominates relevant trainees • UNESCO/CSF delivers the training | • Number of staff trained • % of trainees who successfully passed skill evaluation at the end of the training | Not started | 2021-11-01 | 2021-12-01 | Medium | bar: Q4 2021 Nov M15 to Q4 2021 Dec M16
1.3.2 | QRC | Capacity Development | Monitoring and reporting | Training on OpenEMIS Custom Report Design (2d-2) | This course is designed for QRC IT experts who want to acquire the necessary skills to develop and embed new custom reports into the OpenEMIS Core report module. The training includes practical sessions using SQL and JSON query language to build complex Excel based custom reports in OpenEMIS Core | This training will guide the QRC/EMIS System Administration team on how to develop and embed new custom reports into OpenEMIS without the need for external assistance. | Trainees should have a good understanding of relational database and Structured Query Language (SQL) | • QRC nominates relevant trainees • UNESCO/CSF will deliver the training | • Number of staff trained • % of trainees who successfully passed skill evaluation at the end of the training | Not started | 2022-01-01 | 2022-03-01 | Medium | bar: Q1 2022 Jan M17 to Q1 2022 Mar M19
1.3.3 | QRC | Capacity Development | Monitoring and reporting | Training on OpenEMIS Report Card Design (2d-3) | This course is designed for QRC IT experts who want to acquire the necessary skills to develop and embed new Excel based school report cards into the OpenEMIS Core. | This training will guide the QRC team on how to develop and embed new report cards into OpenEMIS without the need for external assistance. | Trainees should have a good understanding of relational database and Structured Query Language (SQL) | • QRC nominates relevant trainees • UNESCO/CSF delivers the training | • Number of staff trained • % of trainees who successfully passed skill evaluation at the end of the training | Not started | 2022-01-01 | 2022-03-01 | Medium | bar: Q1 2022 Jan M17 to Q1 2022 Mar M19
1.3.4 | QRC | EMIS Feature Enhancement | Monitoring and reporting | Provision of software development services and technical support to develop the additional reports, dashboards and KPIs in OpenEMIS, in line with the needs of MoE staff at all levels (2d-4) | MoE is requesting additional custom reports, indicators and dashboards to be embedded into OpenEMIS Core. Tasks to be completed as described in the Feature Request Sheet and as prioritized in this operational work plan once endorsed by the MoE. | This activity complements activities 1.3.1 and 1.3.2 and 1.3.3 by assisting QRC team in development of custom reports inside OpenEMIS Core. This software development activity, coupled with initial training and on-the-job technical assistance will consolidate skills of the QRC team as well as ensure that all urgent reports are designed and made available in OpenEMIS Core as per MoE's requirements. | Activities 1.3.1, 1.3.2 & 1.3.3 | • QRC collects and consolidates MoE reporting requirements • UNESCO/CSF provides software development services to develop the required reports, indicators and dashboards. • UNESCO/CSF provides technical guidance and backstopping to the QRC team for development of the reports • UNESCO/CSF verifies and finalizes the reports when required for quality assurance | • Number of new custom reports embedded into OpenEMIS Core • Number of new KPIs automated into OpenEMIS Core • Number of new custom dashboards built in OpenEMIS • Number of reports generated by the dynamic reporting tool • School report card is automated into OpenEMIS • % of SDDP KPIs successfully automated into OpenEMIS • % of new custom reports developed by QRC • % of new custom dashboards developed by QRC • % of new KPIs automated by QRC | Ongoing | 2021-01-01 | 2022-03-01 | High | bar: Q1 2021 Jan M5 to Q1 2022 Mar M19
|  |  | No. | SUB-TASKS | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Build a student assessment report that shows all the missing marks entries for the all schools and within any assessment period | The report should show which schools are filling the marks or not. Report should be available to each FD Exam Dept. for follow-up with schools. Report should also be available for each school. A progress overview should be also available central MOE. Find a way to have real-time monitoring of the mark data entry process, given that the DB table is huge and current reports take days to generate. Having a dashboard and detailed report attached to it would help. Current report stopped working (Takes too long) | See Activity 1.3.4 | • Content of the progress report (column headings) to be provided by QRC • See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-08-01 | 2021-09-01 | Medium | bar: Q3 2021 Aug M12 to Q3 2021 Sep M13
|  |  | 2 | Build reports for the Infrastructure module - Report | All infrastructure reports should have additional columns (reports 20, 4, 46, 47 and 50): • The institution status (Active & Inactive) • The institution shift • The infrastructure status (In use & End of Usage) Create a new report for list of Needs | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Awaiting MoE | 2021-01-01 | 2021-09-01 | High | bar: Q1 2021 Jan M5 to Q3 2021 Sep M13
|  |  | 3 | Enhancement of existing report available in OpenEMIS Core | Add new fields to reports no. 25, 26 and 27 (list to be provided by QRC) | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-01-01 | 2021-09-01 | High | bar: Q1 2021 Jan M5 to Q3 2021 Sep M13
|  |  | 4 | Optimization of existing OpenEMIS report queries to reduce processing load | Some reports are currently disabled or not working in the system as they are generating too much processing load on servers. This activity proposes to analyze existing queries and to optimize them when feasible | See Activity 1.3.4 | See Activity 1.3.4 Activity 1.1.1 Activity 1.1.7 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-06-01 | 2021-10-01 | High | bar: Q2 2021 Jun M10 to Q4 2021 Oct M14
|  |  | 5 | Add new custom reports into OpenEMIS | • Number of non-Jordanian students • Number of refugee students • Number of Christians students • Number of students who are studying French language • Others to be provided by QRC (up to 50 in 2 batches) • first batch to be finished by Sep 2021. • second Batch to be finished by Dec 2021 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-04-01 | 2021-12-01 | High | bar: Q2 2021 Apr M8 to Q4 2021 Dec M16
|  |  | 6 | Improvement of the student record export function in school | When exporting students from school, the exported form should include all the student’s information, same as the paper forms filled by schools (The ISO forms), also the same for the Employees and their certifications. • QRC to provide template. • QRC needs to be trained on How to edit those report templates by themselves. • Could be also done as a custom report, provided it shows only the student records attached to the role. | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-07-01 | 2021-09-01 | High | bar: Q3 2021 Jul M11 to Q3 2021 Sep M13
|  |  | 7 | Embed OpenEMIS+ reports into OpenEMIS | Add all the OpenEMIS+ reports into OpenEMIS Core, to be easily accessible by schools | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Awaiting MoE | 2021-08-01 | 2021-10-01 | High | bar: Q3 2021 Aug M12 to Q4 2021 Oct M14
|  |  | 8 | Develop School Formation Cards into OpenEMIS | Add a reporting feature to export the "School Formations Card" report. Template to be provided by Planning Dept. | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-08-01 | 2022-01-01 | High | bar: Q3 2021 Aug M12 to Q1 2022 Jan M17
|  |  | 9 | Develop school 10th grade students classification | Add the School 10th Grade classification report to the custom reports | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Not started | 2021-09-01 | 2022-03-01 | High | bar: Q3 2021 Sep M13 to Q1 2022 Mar M19
|  |  | 10 | Automation of a revised WebGIS input file and API for user authentication | Develop a script enabling EMIS to automatically generate the CSV file required by the WEBGIS application. The script execution frequency could be tuned according to the needs. In addition an API will be developed to enable the WebGIS solution to securely login users by consuming OpenEMIS Core user information such as username and password | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Resolved/Endorsed | 2021-01-01 | 2021-10-01 | High | bar: Q1 2021 Jan M5 to Q4 2021 Oct M14
|  |  | 11 | Enhance OE core APIs to achieve full integration between OE and WebGIS | This activity will ensure the avialbility of the below APIs in OE Core: 1- API-based Integration of OpenEMIS users and their roles (User ID, User Name, User Type, User admin level (MoE, FD or school), School ID, FD ID, User Position and security role) 2- API for schools data (490 column from the current CSV File) 3- API for teachers data (columns from the current CSV File) | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 |  | 2021-11-01 | 2022-01-01 | High | bar: Q4 2021 Nov M15 to Q1 2022 Jan M17
|  |  | 12 | Revision/implementation of ESP M&E framework - KPIs at national level | Up to 20 KPIs | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-06-01 | 2021-09-01 | High | bar: Q2 2021 Jun M10 to Q3 2021 Sep M13
|  |  | 13 | Revision/implementation of ESP M&E framework - KPIs for FD | Up to 20 KPIs | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-06-01 | 2021-09-01 | High | bar: Q2 2021 Jun M10 to Q3 2021 Sep M13
|  |  | 14 | Revision/implementation of ESP M&E framework - KPIs for Schools | Up to 20 KPIs | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-06-01 | 2021-09-01 | High | bar: Q2 2021 Jun M10 to Q3 2021 Sep M13
|  |  | 15 | Automation of SDDP in EMIS | With support from UNESCO, MOE will identify and implement the most appropriate options to automate the SDDP self-review and planning tools, data flow channels and feedback loops to monitor the SDDP at the school, FD and central levels through the development of work flows, indicators, customized dashboards, visualizations and/or reports on OpenEMIS. SDDP automation will be piloted and tested in a sample of schools and FDs and adjusted accordingly | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-06-01 | 2021-10-01 | High | bar: Q2 2021 Jun M10 to Q4 2021 Oct M14
|  |  | 16 | Development of School Report Cards | up to 20 indicators & visualizations | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-01-01 | 2021-12-01 | High | bar: Q1 2021 Jan M5 to Q4 2021 Dec M16
|  |  | 17 | Improvement of the Professional Development Reports | • In Reports > Trainings in the Feature selection, add an item ALL • In Reports > Trainings > Sessions report, add the name of the FD that created the session • In Reports > Trainings > Sessions participants report, add the name of the participant FD that the staff is working in. • In Reports > Trainings, add filters based on course status. when course is approved, add filters for (a) Course (b) Session start date (c) Session end date (d)Field Directorate (with the ability to choose more than one) • In Reports > Trainings > Sessions report, add the number of participants • On Reports > Trainings > Results report, add filters for (a) Training Course (b) Session (with the option All Sessions) (c) Sessions start date (d) Sessions end date (e) Field Directorate (with the ability to choose more than one) (f) Gender • On Reports > Trainings > Results report, add the following fields: (a) Gender (b) FD (c) National ID (d)Employee ID (e) Qualification Specializations • In Reports > Trainings, add a new report named "Trainers' Sessions", with the following fields: (a)Trainer (s) name (b) FD (c) Employee ID (d) National ID (e) Gender (f) Qualification Specializations (g) Session (s) name. Also add filters for (a) FD (b) Trainer name (With the option All) (c) Training course (d) Sessions (with the option All Sessions) (e) Sessions Start date (f) Sessions end date. • In Reports > Trainings > Training needs reports, add the following fields: (a) Staff National ID (b) Staff employee ID (c) Gender • In Reports > Trainings, add a new report named "Training statistics" with the following fields: (a)Training course (b) FD (c) Gender (d) Number of Staff • In Reports > Training, add a new report named "New Employee training card", with report filters (search field by Staff ID (both national and employee ID) or search by name), and with following fields: (a) Staff name (b) Staff national ID (c) Staff employee ID (d) FD (e) Gender (f) Institution (g) Qualification Specializations (h) Training courses that the staff participated (i) The result of the training course | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 |  | 2021-09-01 | 2022-01-01 | Medium | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 18 | School Formation Card Report | • Create a custom report containing all fields required for the School Formulation Card used by the Planning and Research, HR and Finance Department. When data is collected by OpenEMIS, data values will be populated in the report related to Sub-activity 8 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 |  | 2021-09-01 | 2022-01-01 | High | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 19 | Enhance OpenEMIS Core APIs to allign with the required data fields in the school formation card | OpenEMIS Core API will be further enhanced to enable the WebGIS solution to obtain the requested HR data from within the school formation card. | Software Development SoPs | UNESCO WebGIS Expert to provide the template for the required data fields that need to be mapped from the school formation card into WebGIS via the IPA | See Activity 1.3.4 | See Activity 1.3.4 |  | 2022-01-01 | 2022-03-01 | High | bar: Q1 2022 Jan M17 to Q1 2022 Mar M19
|  |  | 20 | Reports for Directorate of Policy and Strategic Planning ( Gender Section, School Formation Department, Educational Statistics Department, School Mapping Department, Department of Policy and Strategic Planning), Property Directorate and Educational Research and Development Directorate | • Students by disability type, gender and grade • Staff by rank, • Ratios of enrollment in vocational education, by gender and by path • Ratios of scholarships by gender • Number of male and female trainees in all training programs • School infrastructure report • Number of principals/teachers by subjects taught, grade, gender, educational qualification, years of service, type of school • Number of non-teaching staff by occupation • Number of sections by type (single/multigrade) and shift • Number of schools with inclusive education programmes • Number of schools by type and availability of key infrastructure types • Report on education programmes offered by schools (and their status) • Number of Ministry employees, according to years of experience, broken down by gender and departments. • Report for the tenth-grade student distribution plan for secondary vocational education branches • Report on school overcrowding (number of students vs nb of seats and available space in classrooms) • Report on school infrastructures by ownership (rented/owned) | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 |  | 2021-09-21 | 2022-01-01 | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 21 | Reports for Directorate of Human Resources (Employment and Staff Department, Staff Performance Review and Analysis Department, Information Department, Vacations Department, End of Service Department, Bonus and Ranks Department | • Report on Technical Status of the Schools (number of students by class and section, number of sections per class, number of teachers by specialization, teacher’s load) • Reports on workflow status • Report on staff records: Job title, date of commencement, Work Center (School, Department), Major and Sub Specialization, Reason for commencement • report on staff dismissal/termination • Report on staff leave • Report on cumulative absences within a time period | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 |  | 2021-09-21 | 2022-01-01 | bar: Q3 2021 Sep M13 to Q1 2022 Jan M17
|  |  | 22 | Development of additional custom reports as requested by QRC | QRC should provide the report templates (up to 10 reports) | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 23 | Development of additional custom reports requested by the Planning and Research department | Planning and Research Department should provide the report templates (up to 10 reports) | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 24 | Development of additional custom reports requested by the Building and Construction Department | Building and Construction Department should provide the report templates (up to 10 reports) | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 25 | Development of additional reports, indicators and dashboards required by the Professional Development Department | up to 10 reports, as per list given by MOE | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | See Activity 1.3.4 | Under Development with OE Lab | 2021-04-01 | 2021-09-01 | High | bar: Q2 2021 Apr M8 to Q3 2021 Sep M13
|  |  | 26 | development of accumulative ABSENCE REPORTS for students and staff on the field directorate and school levels. Development of absence dashboard on the central, field directorate and school levels. | Development of a new report and dashboard | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. | QRC to define requirements of reports and dashboards | refer to Roles and Responsibilities defined in Software Development SOPs | percentage of requests implemented and deployed as per agreed software development scenario |  | 2021-09-01 | 2021-11-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Nov M15
|  |  | 27 | development of ACCUMULATIVE REPORT ON student MARKS per grade and subject on the school, field directorate and central levels | Development of a new report | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. | QRC to define requirements of reports | refer to Roles and Responsibilities defined in Software Development SOPs | percentage of requests implemented and deployed as per agreed software development scenario |  | 2021-09-01 | 2021-12-01 | High | bar: Q3 2021 Sep M13 to Q4 2021 Dec M16
1.3.5 | QRC | EMIS Feature Enhancement | Monitoring and reporting | Provision of software development services to enable MoE to embed custom OpenEMIS Dashboards inside OpenEMIS Core (2d-5) | Develop a feature enabling MOE to develop a dashboard in OpenEMIS Dashboard that contains a filter (list of schools or list of areas). The MOE should have the ability to embed the dashboard in OpenEMIS Core in the Institution Directory page or the single Institution page. Information in the dashboard would then be filtered based on area/institution visited. | This activity proposes that UNESCO/CSF builds the capacity of the QRC relevant team in embedding the dashboards created by them directly within the OpenEMIS Core application. By doing so, stakeholders will have direct and easy access to relevant data visualizations to carry their functions. Eventually, it will ease access to decision-making and monitoring tools for schools and Field Directorates. | NA | • UNESCO/CSF proposes an implementation scenario for the requirement • QRC approves the proposed scenario for requirement • UNESCO/CSF implements the requirement as per agreed scenario • EMIS Technical Committee confirms that feature was implemented as per agreed scenario | Feature(s) of the signed off scenario available in PROD | Not started | 2022-01-01 | 2022-12-01 | Low | bar: Q1 2022 Jan M17 to Q4 2022 Dec M28
1.3.6 | QRC + Planning | EMIS Feature Enhancement | Monitoring and reporting | Development of a dynamic/realtime reporting module (2d-6) | Develop a set of automatically generated anonymized flat data tables that can be queried in real time by MOE stakeholders. An open source software solution for real time data query will be deployed to address this request. | This activity will foster daily use of available data at all levels, by enabling stakeholders to perform real-time exploratory data analysis on thematic areas relevant for their functions. A training is proposed under Activity 2.2.4 | Real time reporting tools on large datasets available in OpenEMIS will require UNESCO Financial and technical support to enable MOE to invest in additional hardware to host the query software. Another option is to rely on cloud services. | • UNESCO/CSF proposes an approach for real-time data querying and identifies hardware requirements for its deployment • MoE EMIS Technical Committee approves the retained approach • MoE procures and setup required hardware • UNESCO/CSF provides open source tools with instructions for their installation on MoE hardware | Feature(s) of the signed off scenario available in PROD | Not started | 2021-11-01 | 2022-06-01 | High | bar: Q4 2021 Nov M15 to Q2 2022 Jun M22
1.3.7 | QRC + Planning | Capacity Development | Monitoring and reporting | Training of trainers on dynamic/realtime reporting module (2d-7) | This activity will provide training on the new dynamic/realtime reporting module for a core MOE team. The core MOE team will be later tasked to train focal points in relevant MOE/FD departments | The retained capacity development approach is to empower a group of core trainers on use of the real-time data analysis tool, who could later cascade trainings across MoE departments and at sub-national levels | NA | • MoE identifies a team of core trainers • UNESCO/CSF delivers the training • MoE develops a training plan for central MoE departments and relevant sub-national stakeholders • MoE implements the training plan | • Number of core MoE staff trained • % of Core MoE trainees who successfully passed skill evaluation at the end of the training • Number of stakeholders trained by the core team at central and sub-national levels | Not started | 2022-06-01 | 2022-08-01 | Medium | bar: Q2 2022 Jun M22 to Q3 2022 Aug M24
1.3.8 | QRC + Planning | Capacity Development | Monitoring and reporting | Training of trainers on OpenEMIS Survey data processing | This training will focus on the use of OpenEMIS Integrator and Excel to process data collected through OpenEMIS Surveys | The retained capacity development approach is to empower a group of core trainers on use of integrator and Excel to process and analyse data collected through OpenEMIS Surveys | NA | • MoE identifies a team of core trainers • UNESCO/CSF delivers the training • MoE develops a training plan for central MoE departments and relevant sub-national stakeholders • MoE implements the training plan | • Number of core MoE staff trained • % of Core MoE trainees who successfully passed skill evaluation at the end of the training • Number of stakeholders trained by the core team at central and sub-national levels | Not started | 2022-01-01 | 2022-05-01 | Medium | bar: Q1 2022 Jan M17 to Q2 2022 MayM21
1.3.9 | QRC + Planning | EMIS Feature Enhancement | Data and information management | Deployment of an enhanced EMIS web portal based on a Content Management System easing dissemination of EMIS information to end-users | This activity will replace the current EMIS portal homepage with an up-to-date Content Management System (CMS) such as Drupal, Joomla or Wordpress to enable MOE to publish a collection of thematic webpages for EMIS data dissemination. Those pages will be made available to EMIS data consumers and offer an easy to access one-stop-shop to centralize, classify and organize statistical and research information related to the education system. | This activity will ease access to information by enabling EMIS data end-users to quickly access relevant links to information relevant for their work. This will be particularly relevant for the Planning and Research Unit to establish a portal centralizing all resources for their operations (links to ESP indicators, Studies and research documents, links to statistical reports for Field Directorates, etc...). The work under this activity will be carried out in a capacity building approach, implemented by UNESCO-CSF. | NA | • MoE identifies a team in charge of the elaboration of the CMS content • UNESCO/CSF supports MoE in identifying the best CMS solution • MoE deploys the CMS on EMIS servers with UNESCO's support • MoE collects end-user's requirements for CMS content • MoE creates and publishes CMS contents based on user's requirements | • A functional CMS platform accessible on emis.MoE.gov.jo • Number of CMS pages created by MoE • % of end-user's information requirements accessible through the CMS | Not started | 2022-01-01 | 2023-01-01 | High | bar: Q1 2022 Jan M17 to Q1 2023 Jan M29
|  |  | No. | SUB-TASKS | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 1 | Establishment of a dedicated online portal for the Planning and Research Unit | The Planning and Research Department is willing to consolidate all relevant statistics and research resources in an easily accessible and centralized place. | This activity proposes to develop a collection of thematic pages on the EMIS portal developed under activity 1.3.9 for central and FD planning and research departments. The portal will contain links or direct access to contents related to ESP indicators, Studies and research documents, links to EMIS reports for Field Directorates | Activity 1.3.9 | • MoE identifies a team in charge of the elaboration of the CMS content • MoE collects end-user's requirements for CMS content • UNESCO/CSF supports MoE in identifying and structuring relevant resources • MoE creates and publishes CMS contents based on user's requirements • MoE shares and validate published content with its target audience | • Number of CMS pages created by MoE • % of end-user's information requirements accessible through the CMS |  | 2022-01-01 | 2022-02-01 | High | bar: Q1 2022 Jan M17 to Q1 2022 Feb M18
|  |  | 2 | Establishment of a dedicated online portal for training resources related to EMIS | EMIS end-users need to access relevant training resources on use of features provided by the EMIS | This activity proposes to develop a collection of thematic pages on the EMIS portal developed under activity 1.3.8 for all EMIS users. The portal will contain all training resources related to EMIS. Training materials already available in existing WIKI portal will be revised and new training resources published as per needs of end-users | Activity 1.3.9 Activity 1.2.3 | • MoE identifies a team in charge of the elaboration of the CMS content • MoE collects end-user's requirements for CMS content • UNESCO/CSF supports MoE in identifying and structuring relevant resources • MoE creates and publishes CMS contents based on user's requirements • MoE shares and validate published content with its target audience | • Number of CMS pages created by MoE • % of end-user's information requirements accessible through the CMS |  | 2022-01-01 | 2022-05-01 | High | bar: Q1 2022 Jan M17 to Q2 2022 MayM21
|  |  | 3 | Establishment of a dedicated online portal for EMIS Operational Manual and Standard Operating Procedures | EMIS end-users need to have a clear idea of their role and responsibilities related to EMIS processes | This activity proposes to publish the operational manual and all Standard Operating Procedure (SOPs) related to EMIS tasks on the EMIS portal through building the capacity of the identified QRC team on managing and elaborating the OpenEMIS CMS portal. | Activity 1.3.9 Activity 2.2.6 Activity 2.2.7 | • MoE identifies a team in charge of the elaboration of the CMS content • MoE collects end-user's requirements for CMS content • UNESCO/CSF supports MoE in identifying and structuring relevant resources • MoE creates and publishes CMS contents based on user's requirements • MoE shares and validate published content with its target audience | • Number of CMS pages created by MoE • % of end-user's information requirements accessible through the CMS |  | 2022-01-01 | 2022-12-01 | High | bar: Q1 2022 Jan M17 to Q4 2022 Dec M28
1.3.10 | QRC + Planning | EMIS Feature Enhancement | Research and evaluation | Import external datasets into the EMIS Data warehouse for relevant Ministry departments | This activity aims at collecting all non OpenEMIS data requirements from key MOE departments and to import them into the EMIS data warehouse when relevant. Prioritized datasets should be linked to the following functions: planning, research, M&E, donor coordination, finance, infrastructure and assets management, HR. | This activity will help MOE organize and classify all relevant statistics for its operations into the centralized datawarehouse, enabling EMIS data end-users to quickly access relevant data. | Activity 1.1.1 | • MoE identifies a team in charge of data warehouse dataset migration • MoE team identifies datasets relevant for key functions in the MoE and agrees on an updating policy for each • UNESCO/CSF supports MoE in selecting datasets relevant for datawarehousing • MoE team imports the datasets into the data warehouse • End-users are trained by the MoE team on dataset retrieval from the datawarehouse | • Number of datasets migrated into the data warehouse for each MoE function • % of data requirements covered by MoE function | Not started | 2021-12-01 | 2022-02-01 | Medium | bar: Q4 2021 Dec M16 to Q1 2022 Feb M18
1.3.11 | QRC | EMIS Feature Enhancement | Monitoring and reporting | Configuration of Real-time dynamic user-defined dashboards and make available in OpenEMIS Core | This activity aims to develop and provide access to realtime dynamic user-defined dashboards within OE Core. This will be achieved through the introduction of a new approach to data analytics with new modules to supplement the existing business architecture. The dashboards and data analytics approach will be piloted before deployment in OpenEMIS Core. Suggested Implementation Plan includes: Needs assessment, Specification of data for user-defined dashboards, System configuration, System piloting, Refinement, Deployment and production, Capacity development on system administration and user training, and Support and maintenance. new approaches to data analytics to provide access to realtime dynamic user-defined dashboards within OE Core. | This activity complements activities 1.3.1 and 1.3.2 and 1.3.3 by assisting QRC team in development of dashboards inside OpenEMIS Core. This software development activity, coupled with initial training and on-the-job technical assistance will consolidate skills of the QRC team. this Capacity Development Approach follows the Software development SOP. | NA | • QRC to lead the needs assessment with direct involvement from UNESCO/CSF. • QRC to provide specifications of data for user-defined dashboards. • UNESCO/CSF to lead the configuration of the system based on the specifications provided by QRC. • UNESCO/CSF to collaborate in piloting the new approach to data analytics with leadership from QRC. • UNESCO/CSF to undertake system refinement based on pilot results. • UNESCO/CSF to support QRC in the deployment of the new modules. • UNESCO/CSF to provide direct capacity building through workshops on the administration and use of the new tools. • UNESCO/CSF to provide ongoing support and maintenance. • UNESCO/CSF to provide a new online KB. • QRC to update the user-defined dashboards. | • Needs assessment report. • Specifications document. • Pilot Report. • System deployed. • Dashboards available key users • a new online KB | Not started | 2021-12-01 | 2022-05-01 | High | bar: Q4 2021 Dec M16 to Q2 2022 MayM21
Expected Result 2 - Improved Data Utilisation for Data-Informed Decision-Making at All Levels
Output 2.1: Improved OpenEMIS Methodological Soundness, Data Integrity, Accuracy and Reliability
2.1.1a | QRC | EMIS Feature Enhancement | Monitoring and reporting | Development of a data quality monitoring module (3a-1) | This activity proposes to develop a full featured data monitoring module inside OpenEMIS Core or as a module within the EMIS web portal, enabling MOE to closely monitor data coverage and data quality by institution/area/module/record type. | This activity will enable MOE to more closely monitor coverage of the data stored in EMIS, as well as it intrasec quality by identifying data outliers. Activity 2.1.2 provides capacity development for use of those features | NA | • UNESCO/CSF proposes an approach for deployment of a data monitoring module within the EMIS • MoE EMIS Technical Committee approves the retained approach • UNESCO/CSF provides open source tools with instructions for their installation on MoE hardware | • Data quality monitoring module available in EMIS | Not started | 2021-11-01 | 2022-01-01 | High | bar: Q4 2021 Nov M15 to Q1 2022 Jan M17
2.1.1b | QRC | EMIS Feature Enhancement | Monitoring and reporting | Development of a data quality monitoring report | Development of a data quality report according to the selected implementation approach of the data quality monbitoring module (2.1.1a) | This activity will enable MOE to more closely monitor coverage of the data stored in EMIS, as well as it intrasec quality by identifying data outliers. Activity 2.1.2 provides capacity development for use of those features | Activity 2.1.1a MoE to provide report requirements | • QRC collects and consolidates MoE reporting requirements • UNESCO/CSF provides software development services to develop the required reports, indicators and dashboards. • UNESCO/CSF provides technical guidance and backstopping to the QRC team for development of the reports • UNESCO/CSF verifies and finalizes the reports when required for quality assurance | • Data quality monitoring report available in EMIS | Not started | 2022-02-01 | 2022-05-01 | High | bar: Q1 2022 Feb M18 to Q2 2022 MayM21
2.1.2 | QRC | Capacity Development | Monitoring and reporting | Training on use of the data quality monitoring module for improved EMIS data accuracy and reliability (3a-2) | A core team of MOE focal points will be trained on use of the data quality monitoring module. This team could train FD level focal points on use of the module | See 2.1.1 | NA | • MoE identifies a team of core trainers • UNESCO/CSF delivers the training • MoE develops a training plan for FD focal points • MoE implements the training plan | • Number of core MoE staff trained • % of Core MoE trainees who successfully passed skill evaluation at the end of the training | Not started | 2022-05-01 | 2022-07-01 | High | bar: Q2 2022 MayM21 to Q3 2022 Jul M23
2.1.3 | QRC | Capacity Development | Monitoring and reporting | Development of Data Auditing Forms (EMIS school statistical forms) inside OpenEMIS (3a-3) | Develop the EMIS school statistical forms to be generated automatically from the OpenEMIS. The automation of these forms facilitates the school data verification process performed by all administrative levels | NA | NA | • QRC develops the form as Surveys in OpenEMIS • UNESCO/CSF provides technical backstopping if necessary | • Data audit forms available in EMIS | Ongoing | 2020-09-01 | 2021-10-01 | High | bar: Q3 2020 Sep M1 to Q4 2021 Oct M14
2.1.4 | QRC | Capacity Development | Monitoring and reporting | Training on OpenEMIS/WebGIS Interfacing (3a-4) | This activity will enable QRC system administration team to maintain the interface between OpenEMIS and WebGIS tools, notably the updating of the tabular file used to interface the two systems | UNESCO/CSF will build the capacity of QRC system administrators to be able to fully manage the integration between OpenEMIS and the WebGIS tools without external assistance | NA | • MoE identifies a team responsible for maintenance of the interface • UNESCO/CSF delivers the training • MoE develops updates the interface as per needs of WebGIS • UNESCO/CSF provides technical backstopping if required | • Interface file updated with latest statistics from EMIS | Ongoing | 2020-09-01 | 2021-10-01 | Critical | bar: Q3 2020 Sep M1 to Q4 2021 Oct M14
2.1.5 | QRC | Capacity Development | Monitoring and reporting | Training on maintenance of the mini-dashboard (https://data.emis.MoE.gov.jo/mini-dashboard/) (3a-5) | This activity will enable QRC system administration team to update and maintain independently the mini-dashboard components delivered under the first phase of the EMIS programme | UNESCO/CSF will build the capacity of QRC system administrators to be able to fully manage the mini-dashboard without external assistance | NA | • MoE identifies a team responsible for maintenance of the interface • UNESCO/CSF delivers the training • UNESCO/CSF provides technical backstopping if required • MoE updates mini-dashboard content with support from UNESCO/CSF | • Number of MoE staff trained • mini-dashboard updated with current year data | Completed | 2020-09-01 | 2021-02-01 | High | bar: Q3 2020 Sep M1 to Q1 2021 Feb M6
2.1.6 | QRC+Planning | Capacity Development | Data and information management | Establishment of a digital EMIS Help Desk for provision of technical assistance to FDs and Schools on EMIS use (3a-6) | This activity aims at reactivating a digitalized EMIS Help Desk in MOE/QRC to assist EMIS end-users when required | This activity will enable MoE to provide improved support to EMIS end-users and to systematically monitor support provided to EMIS field operations | NA | • MoE identifies a team responsible for establishment of the Help Desk • MoE identifies the most relevant technical options to setup a help desk with UNESCO/CSF guidance and technical backstopping • MoE procures the technical solution retained • Solution provider delivers assistance for the setup of the help desk solution and also training to MoE core responsible team on the use of the helpdesk system • MoE plans and delivers cascade training modality to build the capacity of the MoE Helpdesk users at all levels with UNESCO/CSF technical backstopping • MoE Help Desk is advertised and activated | • Availability of a digital help desk service for EMIS in MoE | Not started | 2022-02-01 | 2022-05-01 | Medium | bar: Q1 2022 Feb M18 to Q2 2022 MayM21
2.1.7 | QRC | EMIS Feature Enhancement | Data and information management | Automate the data exchange between OpenEMIS with UNRWA EMIS | This activity aims at utilizing OpenEMIS APIs to automate the data exchange OE and UNRWA EMIS Steps to integrate UNRWA data into OpenEMIS: 1. Indentify what data is required from the UNRWA EMIS 2. Check and confirm that APIs exist in OpenEMIS to accept these data from the UNRWA EMIS 3. Share the details of the data required and the OpenEMIS Core APIs with UNRWA 4. UNRWA to update the EMIS to send data to OpenEMIS Core | this activity will strengthen MoE capacity to perform data exchange excercises with other educatioanl systems through utilizing OpenEMIS API feature | Activity 1.1.1 Activity 1.1.4a Indentify what data is required from the UNRWA EMIS UNRWA to update the EMIS to send data to OpenEMIS Core | • MoE to idietifies the required data fields from UNRWA EMIS • MoE to check and confirm that APIs exist in OpenEMIS to accept these data from the UNRWA EMIS • MoE to share the details of the data required and the OpenEMIS Core APIs with UNESCO/CSF backstopping. • UNRWA to update the EMIS to send data to OpenEMIS Core | MoE's endoresement of succesful data exchange between OpenEMIS and UNRWA EMIS | Not started | 2021-12-01 | 2022-02-01 | High | bar: Q4 2021 Dec M16 to Q1 2022 Feb M18
2.1.8 | QRC, DCU, Planning Department | EMIS Feature Enhancement | Data and information management | Enhancing OpenEMIS students module to align with UNHCR refugess data model | this activity aims at improving the quality of coverage, reliabity of OpenEMIS refugee students data 1- MoE to provide full requirements in relation to the data fields to be added to OpenEMIS and associated validations, to achieve alignemnt with UNHCR data model. 2- UNESCO/CSF to develop the additional fields into OE through following the agreed Sw Dev SoPs. | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. | Activity 1.1.1 | refer to Roles and Responsibilities defined in Software Development SOPs | percentage of requests implemented and deployed as per agreed software development scenario |  | 2022-01-01 | 2022-04-01 | Medium | bar: Q1 2022 Jan M17 to Q2 2022 Apr M20
2.1.9 | DCU | EMIS Feature Enhancement | Data and information management | Enhancement of OpenEMIS to TDSM Depolyment | this activity aims at enhancement of OpenEMIS to TDSM Model developed by Irex | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. |  | refer to Roles and Responsibilities defined in Software Development SOPs |  |  | 2021-08-01 | 2022-02-01 | High | bar: Q3 2021 Aug M12 to Q1 2022 Feb M18
|  |  | No. | SUB-TASKS | Comments | Capacity Development Approach | Prerequisites | Roles and Responsibilities | Measure of Achievement
|  |  | 2.1.9.1 | Link the TDSM (Teacher/Demand Supply Model) with OpenEMIS Core data in a way similar to the Mini Dashboard | this activity aims at linking TDSM Module with OpenEMIS Core data in a way similar to the Mini Dashboard to show real-time data | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. |  | refer to Roles and Responsibilities defined in Software Development SOPs | MoE's endoresment of the successful data exchange between OpenEMIS and TDSM Model |  | 2021-08-01 | 2021-09-01 | Critical | bar: Q3 2021 Aug M12 to Q3 2021 Sep M13
|  |  | 2.1.9.2 | Integrate the TDSM (Teacher/Demand Supply Model) as an OpenEMIS Core feature/module | this activity aims at deploying TDSM Model as a feature in OpenEMIS Core to show real-time data | This activity puts into practice the Software Development SOPs. The EMIS software development process will be led by MoE QRC to progressively increase EMIS software development management capacity of the MoE. | Irex handing over the Software Module CSF requires a duration of 2 months to start the activity after Irex complete the software development | refer to Roles and Responsibilities defined in Software Development SOPs | MoE's endoresment of the successful data exchange between OpenEMIS and TDSM Model |  | 2021-11-01 | 2022-02-01 | High | bar: Q4 2021 Nov M15 to Q1 2022 Feb M18
Output 2.2: MoE Staff Capacities are Strengthened to Undertake Analysis of Education Data for Decision Making using OpenEMIS
Improving MoE central level capacities for undertaking analysis of education data for decision-making
2.2.1 | QRC+ Planning | Capacity Development | Monitoring and reporting | Refresher Trainings for central MoE departments on use of OpenEMIS for informed decision making (3b-1) | This activity aims at raising awareness about data availability in OpenEMIS and to sensibilize every MOE department on his role(s) and responsibilities for recording and updating OpenEMIS datasets relevant to them. The trainings will notably focus on the use of all existing reporting features available in OpenEMIS to inform decision making at central level | UNESCO/CSF will build the capacity of the MoE staff to be fully aware of the existing data/reports available in EMIS and about their role in ensuring data quality. | 2.2.11 | • MoE identifies a team responsible for the delivery of the trainings • MoE identifies the MoE departments to be trained and EMIS priority topics linked to them • MoE with UNESCO/CSF prepare training plans for the refresher training programme • UNESCO/CSF provides the required technical assistance during the trainings. • The MoE Trainers deliver the refresher training sessions to target Departments | • Number of MoE staff trained by central MoE team | Not started | 2021-11-01 | 2022-05-01 | Critical | bar: Q4 2021 Nov M15 to Q2 2022 MayM21
2.2.2 | Planning | Capacity Development | Planning and budgeting | Refresher Training for central MoE departments on use of OpenEMIS Monitoring for strategic planning as well as its capability to be used as a technical assistance tracking tool (3b-2) | This training will focus on the use of OpenEMIS to monitor and report on ESP implementation and any other plans or projects | UNESCO/CSF will provide refresher capacity building to the relevant MoE staff on utilizing the existing ESP/Project monitoring EMIS solutions available in EMIS. Another set of trainings to be planned/provided to MoE DCU relevant staff on using OpenEMIS monitoring tool as a technical assistance tracking tool. | NA | • MoE identifies a team responsible for the delivery of the trainings • MoE identifies the MoE departments to be trained and priority topics linked to them • The MoE Trainers deliver the refresher training sessions with backstopping from UNESCO | • Number of MoE staff trained by central MoE team | Completed | 2020-12-01 | 2020-12-01 | Critical | bar: Q4 2020 Dec M4
2.2.3 | QRC | Capacity Development | Data and information management | Training of a MoE core team on OpenEMIS Mobile applications (OpenEMIS Survey, OpenEMIS Classroom, OpenEMIS Staffroom) (3b-3) | This training will focus on the use of existing OpenEMIS mobile applications: OpenEMIS Survey, OpenEMIS Classroom, OpenEMIS StaffRoom) | UNESCO/CSF will build the capacity of the MoE on the use of alternative mobile devices to access EMIS features, which will ease interactions of end-users with EMIS, improving data quality | NA | • MoE identifies a team of trainees • UNESCO/CSF delivers the training • MoE develops a training plan to cascade the training • MoE implements the training plan | • Number of MoE staff trained • Availability of a training plan on mobile apps | Completed | 2021-04-01 | 2021-07-01 | Low | bar: Q2 2021 Apr M8 to Q3 2021 Jul M11
2.2.4 | QRC+Planning | Capacity Development | Monitoring and reporting | Training and on-the-job technical assistance services to assist a MoE core team on updating existing data visualizations (ErfKE KPIs and dashboard, ESP Kpis and Dashboards) (3b-4) | This activity will allow MOE to update all existing EMIS data visualization tools with up-to-date statistics from the EMIS | This activity will entail refresher trainings provided to the MoE by UNESCO/CSF to update the existing EMIS data visualizations, which already provide detailed insights about education dynamics. However, those need to be updated to be relevant for end-users | NA | • MoE identifies a team of trainees • UNESCO/CSF delivers a refresher's training • MoE updates existing visualizations with technical backstopping from UNESCO/CSF | • Number of MoE staff trained • % of existing data visualization showing lasted data available | Completed | 2021-04-01 | 2021-04-01 | High | bar: Q3 2020 Sep M1 to Q3 2021 Aug M12
2.2.5 | QRC+Planning | Capacity Development | Data and information management | Update the existing yearly EMIS operational Manual (1e) | EMIS Operational Manual is a normative document will be a well-formulated reference for key stakeholders using/relying on EMIS, which describes in a structured and concise way the critical EMIS activities occurring throughout a given scholastic year. These activities relate to the preparatory phase and launch of the EMIS data collection campaign, data collection at the school level, monitoring of field operations and quality control procedures, data transformation and analysis of EMIS data and publication/release and dissemination of yearly statistical reports within and outside of the MoE. The manual should also describe MoE internal workflows (1) for EMIS daily transactions occurring school/regional/central levels and (2) for management/enhancement of statistical nomenclatures and questionnaires/data collections forms used by the EMIS based on data consumer’s requirements. | MoE will take lead in the update process of the EMIS Operational manual. UNESCO/CSF will provide the required support to make sure the EMIS Operational Manual is regularly updated to reflect changes made to the EMIS during the programme, and that it's properly linked to the developed EMIS policy. | NA | • MoE identifies a team in charge of updating the EMIS Operational Manual • MoE organizes consultations with stakeholders involved in EMIS operations to validate and update EMIS workflows/timelines • MoE updates the Operational Manual • EMIS Operational Manual is published on the EMIS portal and distributed to EMIS stakeholders • UNESCO/CSF provides the required technical guidance and quality assurance to ensure proper update of the manual and its linkages to the EMIS policy document. | • Availability of an up-to-date EMIS Operational Plan • % of EMIS users using the EMIS Operational Plan to conduct EMIS related activities | Not started | 2022-01-01 | 2022-09-01 | High | bar: Q1 2022 Jan M17 to Q3 2022 Sep M25
2.2.6 | QRC+Planning | Capacity Development | Data and information management | Development of EMIS standard operating procedures (3b-5) | This activity further operationalizes the EMIS operational manual by developing concise standard operating procedures on each key EMIS functionalities. Theses SOPs would be used to guide each actor involved in EMIS operations and measure conformity of operations with standards | EMIS SOPs will ensure EMIS tasks are rightly performed by EMIS stakeholders | NA | • MoE identifies a team in charge of updating the EMIS SOPs • MoE organizes consultations with stakeholders involved in EMIS operations to validate SOPs with the support of UNESCO/CSF • MoE updates the SOPs with UNESCO/CSF guidance and backstopping • EMIS SOPs published on the EMIS portal and distributed to EMIS stakeholders | • Availability of up-to-date SOPs • % of EMIS users using the SOPS to conduct EMIS related activities | Not started | 2022-01-01 | 2022-10-01 | High | bar: Q1 2022 Jan M17 to Q4 2022 Oct M26
2.2.7 | UNESCO | Capacity Development | Data and information management | Supporting the revision or development of Terms of Reference for EMIS users at central, regional and school levels (3b-6) | Responsibility chain from schools, FD, central MOE for reporting in OpenEMIS is not clear and often concentrated to very few actors. | This activity proposes to organize cascading workshops at school/FD/Governorate/central levels to identify and build consensus on optimal EMIS roles and responsibilities for each stakeholder. Outputs of this participatory activity should then be used by MOE to incorporate EMIS tasks into ToRs of each stakeholder. Cascading workshops would be also organized by MOE after the TOR revisions to sensibilize personnel on their new roles and responsibilities | NA | • UNESCO/CSF provides generic terms of refence for each EMIS user profile • MoE/Planning and MoE/QRC conduct workshops with logistical backstopping from UNESCO • MoE updates the ToRs of all EMIS users | • Number of MoE positions embedding clear EMIS ToRs at each level (central MoE/governorate/FD/School) | Ongoing | 2021-04-21 | 2021-12-01 | High | bar: Q2 2021 Apr M8 to Q4 2021 Dec M16
Improving FD level capacities for undertaking analysis of education data for decision-making
2.2.8 | Planning | Capacity Development | Monitoring and reporting | Training for FDs on use of OpenEMIS for informed decision making (3c-1) | This training will focus on the use of all existing reporting features available in OpenEMIS to inform decision making at central level and update FD users on OE Core features relevant for FDs | MoE core trainers will provide trainings for the MoE FD staff on the use of the existing OpenEMIS reporting features. UNESCO/CSF stands by to provide necessary support when/if needed. | 2.2.11 | • MoE with the support of UNESCO/CSF prepare the training plans for this activity. • MoE identifies a core team responsible for the delivery of the trainings. Logistics and administrative costs are covered by the MoE. • MoE identifies the FD departments to be trained and EMIS priority topics linked to them • The MoE Trainers deliver the refresher training sessions to target FD Departments | • Number of FD Departments trained | Not started | 2022-07-01 | 2022-09-01 | High | bar: Q3 2020 Sep M1 to Q3 2021 Aug M12; Q3 2022 Jul M23 to Q3 2022 Sep M25
2.2.9 | Planning | Capacity Development | Planning and budgeting | Training for FDs on use of OpenEMIS Monitoring for strategic planning | This training will focus on the use of OpenEMIS to monitor and report on ESP implementation | MoE core trainers will provide trainings for the MoE FD staff on the use existing ESP/Project monitoring EMIS solutions available in EMIS and about their role in updating this information. UNESCO/CSF stands by to provide necessary support when/if needed. | 2.2.11 | • MOE identifies a team responsible for the delivery of the trainings • MOE identifies the FD Departments to be trained and priority topics linked to them • The MOE Trainers deliver the refresher training sessions with backstopping from UNESCO | • Number of FD Departments trained | Not started | 2022-07-01 | 2022-09-01 | High | bar: Q3 2020 Sep M1 to Q3 2021 Aug M12; Q3 2022 Jul M23 to Q3 2022 Sep M25
Improving school level capacities for undertaking analysis of education data for decision-making
2.2.10 | Planning | Capacity Development | Data and information management | Conceptualization of school report cards relevant for schools (2d) | School report cards are generally a one-page summary document displaying education indicators using visual info graphics such as tables, graphs, maps and images. School Report Cards will provide information at a very decentralized level, on school inputs (e.g. number of students, teachers, textbooks, expenditures), processes (e.g. repetition and dropout rates, parental and community involvement, school climate), and outputs (e.g. promotion and graduation rates, test scores). | This activity proposes a set of participatory consultations with the MoE relevant staff to finalize the concept of the school report card and agree on its template. UNESCO/CSF will provide the technical assistance to develop the required feature on OpenEMIS Core school module. | NA | • MoE with UNESCO/CSF arrange consultations with the relevant MoE staff/departments to confirm on the initial concept and template of the required school report card. • UNESCO/CSF develops the school report as per the endorsed final concept. | • School report card template approved by MoE | completed | 2021-03-01 | 2021-04-01 | High | bar: Q1 2021 Mar M7 to Q2 2021 Apr M8
2.2.11 | Planning | Capacity Development | Monitoring and reporting | Preparation of a national training plan for use of EMIS at national level for decision-making (3d-1) | Preparation of a comprehensive training plan for schools on use of EMIS at school level to foster informed decision-making | NA | NA | • MoE identifies a team responsible for development of a training plan • MoE develops a training plan with technical advice from UNESCO | • Availability of a Training Plan | Not started | 2022-06-01 | 2022-07-01 | High | bar: Q2 2022 Jun M22 to Q3 2022 Jul M23
2.2.12 | Planning | Capacity Development | Monitoring and reporting | Training for school trainers on use of OpenEMIS for informed decision making (3d-1) | This activity corresponds to the implementation of the training plan developed under 2.2.11 which will be implemented by the MoE relevant nominated teams with the technical guidance and backstopping provided by UNESCO/CSF | Capacity building on using OpenEMIS for informed decision making will be provided by the MoE relevant teams to the schools staff in a cascading manner. | 2.2.11 major software development features at school level should be completed and endorsed | • MoE with the support of UNESCO/CSF prepare the training plans for this activity. • MoE is responsible for the delivery of the training plan activities including logistics. • Selected stakeholders deliver training plan activities • MoE with UNESCO/CSF monitor quality of the delivery • A consolidated report on outcomes of the training plan is produced by MoE | • Availability of a training report | Not started | 2022-07-01 | 2022-09-01 | High | bar: Q3 2022 Jul M23 to Q3 2022 Sep M25
2.2.13 | Planning | Capacity Development | Monitoring and reporting | SDDP automation pilot | This activity will pilot the SDDP automation done under activity 1.3.4 in a sample of schools and FDs. Feedback from pilot participants will enable MOE to refine the SDDP automation procedures | Collection of end-user's feedback on SDDP automation will ensure that SDDP automation is feasible and scalable | Activity 1.3.4 (SDDP Automation) | • MoE with the support of UNESCO/CSF prepare the pilot plans for this activity. • MOE identifies stakeholders responsible for organization of the pilot activities • Selected stakeholders implement pilot activities • MoE with UNESCO/CSF monitor quality of the pilot delivery • A consolidated report on outcomes of the pilot is produced by MOE to inform tuning of the SDDP automation • UNESCO/CSF provide technical assistance to adjust SDDP automation based on pilot findings | • Availability of a pilot report | Not started | 2021-10-01 | 2022-01-01 | High | bar: Q4 2021 Oct M14 to Q1 2022 Jan M17